## 1Requisition_Tracking-Summary63
| Requistion Tracking - Summary | Requistion Tracking - Summary | Requistion Tracking - Summary | Requistion Tracking - Summary | Requistion Tracking - Summary | Requistion Tracking - Summary | Requistion Tracking - Summary | Requistion Tracking - Summary | Requistion Tracking - Summary | Requistion Tracking - Summary | Requistion Tracking - Summary
| From Date : 30/07/2020 To date: 31/07/2020 | From Date : 30/07/2020 To date: 31/07/2020 | From Date : 30/07/2020 To date: 31/07/2020 | From Date : 30/07/2020 To date: 31/07/2020 | From Date : 30/07/2020 To date: 31/07/2020 | From Date : 30/07/2020 To date: 31/07/2020 | From Date : 30/07/2020 To date: 31/07/2020 | From Date : 30/07/2020 To date: 31/07/2020 | From Date : 30/07/2020 To date: 31/07/2020 | From Date : 30/07/2020 To date: 31/07/2020 | From Date : 30/07/2020 To date: 31/07/2020
| Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1
| Total Records: 11 Records 1 to 11 | Total Records: 11 Records 1 to 11 | Total Records: 11 Records 1 to 11 | Total Records: 11 Records 1 to 11 | Total Records: 11 Records 1 to 11 | Total Records: 11 Records 1 to 11 | Total Records: 11 Records 1 to 11 | Total Records: 11 Records 1 to 11 | Total Records: 11 Records 1 to 11 | Total Records: 11 Records 1 to 11 | Total Records: 11 Records 1 to 11
Project | Material_Name | Unit_Name | ReqSr_No | Requisition_Date | Requirement_Date | Qty | APP_Qty | PO_Qty | User_Name | Status | Remark
Atlante | Control Panel For 10 hp,3ph submersible pump | Nos | 1702 | 2020-07-30 | 2020-08-01 | 1 | 1 | 0 | pranav.m | Completed
Atlante | Green House Pipe-3" | Mtr | 1703 | 2020-07-30 | 2020-08-01 | 60 | 60 | 0 | pranav.m | Completed
Atlante | Laxmi Lada Dewatering submersible pump set | Nos | 1704 | 2020-07-30 | 2020-08-02 | 1 | 1 | 0 | pranav.m | Completed
Atlante | Nylon Rope (For Pump) | Rft | 1705 | 2020-07-30 | 2020-08-01 | 50 | 50 | 0 | pranav.m | Completed
Atlante | Plumbing Material (For Pump Set) | Set | 1706 | 2020-07-30 | 2020-08-01 | 1 | 1 | 0 | pranav.m | Completed
Atlante | Pump installtion | Job | 1707 | 2020-07-30 | 2020-08-01 | 1 | 1 | 0 | pranav.m | Completed
Atlante | Submersible Cable 2.5 Sq.mm X 3 Core | Mtr | 1708 | 2020-07-30 | 2020-08-01 | 60 | 60 | 0 | pranav.m | Completed
Atlante | Nitobond | Ltr | 1709 | 2020-07-30 | 2020-08-01 | 60 | 60 | 0 | pranav.m | Completed
Atlante | Slum Cone | Nos | 1710 | 2020-07-30 | 2020-08-02 | 1 | 1 | 0 | pranav.m | Completed
Atlante | BASF 850i | Ltr | 1711 | 2020-07-30 | 2020-08-01 | 250 | 250 | 0 | pranav.m | Completed
Atlante | 63 AMP 3PHASE HOME PROTECTOR | Nos | 1712 | 2020-07-30 | 2020-08-02 | 1 | 1 | 0 | pranav.m | Completed