## 1Requisition_Tracking-Summary63
| Requistion Tracking - Summary | Requistion Tracking - Summary | Requistion Tracking - Summary | Requistion Tracking - Summary | Requistion Tracking - Summary | Requistion Tracking - Summary | Requistion Tracking - Summary | Requistion Tracking - Summary | Requistion Tracking - Summary | Requistion Tracking - Summary | Requistion Tracking - Summary
| From Date : 08/08/2020 To date: 08/09/2020 | From Date : 08/08/2020 To date: 08/09/2020 | From Date : 08/08/2020 To date: 08/09/2020 | From Date : 08/08/2020 To date: 08/09/2020 | From Date : 08/08/2020 To date: 08/09/2020 | From Date : 08/08/2020 To date: 08/09/2020 | From Date : 08/08/2020 To date: 08/09/2020 | From Date : 08/08/2020 To date: 08/09/2020 | From Date : 08/08/2020 To date: 08/09/2020 | From Date : 08/08/2020 To date: 08/09/2020 | From Date : 08/08/2020 To date: 08/09/2020
| Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1 | Page 1 of 1
| Total Records: 285 Records 1 to 285 | Total Records: 285 Records 1 to 285 | Total Records: 285 Records 1 to 285 | Total Records: 285 Records 1 to 285 | Total Records: 285 Records 1 to 285 | Total Records: 285 Records 1 to 285 | Total Records: 285 Records 1 to 285 | Total Records: 285 Records 1 to 285 | Total Records: 285 Records 1 to 285 | Total Records: 285 Records 1 to 285 | Total Records: 285 Records 1 to 285
Project | Material_Name | Unit_Name | ReqSr_No | Requisition_Date | Requirement_Date | Qty | APP_Qty | PO_Qty | User_Name | Status | Remark
41 Estera | 065 Divertor - 40mm Carterage | Nos. | 1359 | 2020-08-31 | 1900-01-01 | 8 | 8 | 0 | Rakesh Shinde | Completed
41 Estera | 065 Divertor - 40mm Carterage | Nos. | 1360 | 2020-08-31 | 1900-01-01 | 8 | 8 | 0 | Rakesh Shinde | Completed
41 Estera | ACO- Nahani Trap Quadrato | Nos | 1361 | 2020-08-31 | 1900-01-01 | 4 | 4 | 0 | Rakesh Shinde | Completed
41 Estera | ACO- Nahani Trap Quadrato | Nos | 1362 | 2020-08-31 | 1900-01-01 | 4 | 4 | 0 | Rakesh Shinde | Completed
41 Estera | Agri. PVC Elbow 110mm. H/W | NO | 1363 | 2020-08-31 | 1900-01-01 | 16 | 16 | 0 | Rakesh Shinde | Completed
41 Estera | CI Chair Bracket For wallhung - Pair | Pair | 1364 | 2020-08-31 | 1900-01-01 | 8 | 8 | 0 | Rakesh Shinde | Completed
41 Estera | CI Chair Bracket For wallhung - Pair | Pair | 1365 | 2020-08-31 | 1900-01-01 | 8 | 8 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC Brass Elbow 1/2" | Nos. | 1366 | 2020-08-31 | 1900-01-01 | 64 | 64 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC Brass Elbow 1/2" | Nos. | 1367 | 2020-08-31 | 1900-01-01 | 64 | 64 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC Elbow 1/2" | Nos. | 1368 | 2020-08-31 | 1900-01-01 | 108 | 108 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC Elbow 1/2" | Nos. | 1369 | 2020-08-31 | 1900-01-01 | 100 | 100 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC Elbow 11/4" | Nos. | 1370 | 2020-08-31 | 1900-01-01 | 64 | 64 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC Elbow 11/4" | Nos. | 1371 | 2020-08-31 | 1900-01-01 | 16 | 16 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC End Cap 1/2" | Nos. | 1372 | 2020-08-31 | 1900-01-01 | 20 | 20 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC End Cap 1/2" | Nos. | 1373 | 2020-08-31 | 1900-01-01 | 20 | 20 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC End Cap 11/4" | Nos. | 1374 | 2020-08-31 | 1900-01-01 | 8 | 8 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC End Cap 11/4" | Nos. | 1375 | 2020-08-31 | 1900-01-01 | 8 | 8 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC End Plug 1/2" | Nos. | 1376 | 2020-08-31 | 1900-01-01 | 64 | 64 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC End Plug 1/2" | Nos. | 1377 | 2020-08-31 | 1900-01-01 | 64 | 64 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC FTA Brass 11/4" | Nos. | 1378 | 2020-08-31 | 1900-01-01 | 8 | 8 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC FTA Brass 11/4" | Nos. | 1379 | 2020-08-31 | 1900-01-01 | 8 | 8 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC MTA Brass 1/2" | Nos. | 1380 | 2020-08-31 | 1900-01-01 | 32 | 32 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC MTA Brass 1/2" | Nos. | 1381 | 2020-08-31 | 1900-01-01 | 32 | 32 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC MTA Brass 11/4" | Nos. | 1382 | 2020-08-31 | 1900-01-01 | 8 | 8 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC MTA Brass 11/4" | Nos. | 1383 | 2020-08-31 | 1900-01-01 | 8 | 8 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC Pipe 1/2" SDR-11 (3 Mtr.) | Nos. | 1384 | 2020-08-31 | 1900-01-01 | 34 | 34 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC Pipe 1/2" SDR-11 (3 Mtr.) | Nos. | 1385 | 2020-08-31 | 1900-01-01 | 30.8 | 30.8 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC Pipe11/4" SDR-11 (3 Mtr.) | Nos. | 1386 | 2020-08-31 | 1900-01-01 | 8.8 | 8.8 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC Pipe11/4" SDR-11 (3 Mtr.) | Nos. | 1387 | 2020-08-31 | 1900-01-01 | 4 | 4 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC Solvent Soilibond 1000ml. - Tin. | Tin | 1388 | 2020-08-31 | 1900-01-01 | 0.6 | 0.6 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC Solvent Soilibond 1000ml. - Tin. | Tin | 1389 | 2020-08-31 | 1900-01-01 | 6 | 6 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC Tee 1/2" | Nos. | 1390 | 2020-08-31 | 1900-01-01 | 40 | 40 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC Tee 1/2" | Nos. | 1391 | 2020-08-31 | 1900-01-01 | 32 | 32 | 0 | Rakesh Shinde | Completed
41 Estera | Flush valve Consiled 1 1/4" Brass (Jaquar) | Nos. | 1392 | 2020-08-31 | 1900-01-01 | 8 | 8 | 0 | Rakesh Shinde | Completed
41 Estera | Flush valve Consiled 1 1/4" Brass (Jaquar) | Nos. | 1393 | 2020-08-31 | 1900-01-01 | 8 | 8 | 0 | Rakesh Shinde | Completed
41 Estera | Hold Tite 500 gm | Tin | 1394 | 2020-08-31 | 1900-01-01 | 1.2 | 1.2 | 0 | Rakesh Shinde | Completed
41 Estera | Multi Floor trap | No. | 1395 | 2020-08-31 | 1900-01-01 | 16 | 16 | 0 | Rakesh Shinde | Completed
41 Estera | Multi Floor trap | No. | 1396 | 2020-08-31 | 1900-01-01 | 12 | 12 | 0 | Rakesh Shinde | Completed
41 Estera | Nails Plumbing 2" | Kg | 1397 | 2020-08-31 | 1900-01-01 | 4 | 4 | 0 | Rakesh Shinde | Completed
41 Estera | Nails Plumbing 2" | Kg | 1398 | 2020-08-31 | 1900-01-01 | 4 | 4 | 0 | Rakesh Shinde | Completed
41 Estera | Pipe Agri. 2" x 20' - 6 kgs. | NO | 1399 | 2020-08-31 | 1900-01-01 | 1.8 | 1.8 | 0 | Rakesh Shinde | Completed
41 Estera | Pipe Agri. 2" x 20' - 6 kgs. | NO | 1400 | 2020-08-31 | 1900-01-01 | 4 | 4 | 0 | Rakesh Shinde | Completed
41 Estera | Pipe Agri. 3" x 20' - 4 kgs. | NO | 1401 | 2020-08-31 | 1900-01-01 | 6.48 | 6.48 | 0 | Rakesh Shinde | Completed
41 Estera | Pipe Agri. 3" x 20' - 4 kgs. | NO | 1402 | 2020-08-31 | 1900-01-01 | 8.8 | 8.8 | 0 | Rakesh Shinde | Completed
41 Estera | PVC Agri Bushing 50mm x 40mm - 10 Kgs | Nos | 1403 | 2020-08-31 | 1900-01-01 | 12 | 12 | 0 | Rakesh Shinde | Completed
41 Estera | PVC Agri Bushing 50mm x 40mm - 10 Kgs | Nos | 1404 | 2020-08-31 | 1900-01-01 | 16 | 16 | 0 | Rakesh Shinde | Completed
41 Estera | PVC Agri Elbow 40mm - 10 kgs | NO | 1405 | 2020-08-31 | 1900-01-01 | 8 | 8 | 0 | Rakesh Shinde | Completed
41 Estera | PVC Agri Elbow 50mm - 10 kgs | NO | 1406 | 2020-08-31 | 1900-01-01 | 4 | 4 | 0 | Rakesh Shinde | Completed
41 Estera | PVC Agri Elbow 50mm - 10 kgs | NO | 1407 | 2020-08-31 | 1900-01-01 | 4 | 4 | 0 | Rakesh Shinde | Completed
41 Estera | PVC Agri End Cap 40 mm - 10 kgs | NO | 1408 | 2020-08-31 | 1900-01-01 | 16 | 16 | 0 | Rakesh Shinde | Completed
41 Estera | PVC Agri End Cap 40 mm - 10 kgs | NO | 1409 | 2020-08-31 | 1900-01-01 | 16 | 16 | 0 | Rakesh Shinde | Completed
41 Estera | PVC Agri End Cap 50 mm - 10 kgs | NO | 1410 | 2020-08-31 | 1900-01-01 | 12 | 12 | 0 | Rakesh Shinde | Completed
41 Estera | PVC Agri End Cap 50 mm - 10 kgs | NO | 1411 | 2020-08-31 | 1900-01-01 | 4 | 4 | 0 | Rakesh Shinde | Completed
41 Estera | PVC Agri Plain Long Bend 40mm - 10 kgs | No. | 1412 | 2020-08-31 | 1900-01-01 | 12 | 12 | 0 | Rakesh Shinde | Completed
41 Estera | PVC Agri Plain Long Bend 40mm - 10 kgs | No. | 1413 | 2020-08-31 | 1900-01-01 | 8 | 8 | 0 | Rakesh Shinde | Completed
41 Estera | PVC Agri Plain Tee 75mm 4 Kg. | No. | 1414 | 2020-08-31 | 1900-01-01 | 4 | 4 | 0 | Rakesh Shinde | Completed
41 Estera | PVC Agri Plain Tee 75mm 4 Kg. | No. | 1415 | 2020-08-31 | 1900-01-01 | 4 | 4 | 0 | Rakesh Shinde | Completed
41 Estera | 065 Divertor - 40mm Carterage | Nos. | 1416 | 2020-08-31 | 1900-01-01 | 8 | 8 | 0 | Rakesh Shinde | Completed
41 Estera | 065 Divertor - 40mm Carterage | Nos. | 1417 | 2020-08-31 | 1900-01-01 | 8 | 8 | 0 | Rakesh Shinde | Completed
41 Estera | ACO- Nahani Trap Quadrato | Nos | 1418 | 2020-08-31 | 1900-01-01 | 4 | 4 | 0 | Rakesh Shinde | Completed
41 Estera | ACO- Nahani Trap Quadrato | Nos | 1419 | 2020-08-31 | 1900-01-01 | 4 | 4 | 0 | Rakesh Shinde | Completed
41 Estera | Agri. PVC Elbow 110mm. H/W | NO | 1420 | 2020-08-31 | 1900-01-01 | 16 | 16 | 0 | Rakesh Shinde | Completed
41 Estera | CI Chair Bracket For wallhung - Pair | Pair | 1421 | 2020-08-31 | 1900-01-01 | 8 | 8 | 0 | Rakesh Shinde | Completed
41 Estera | CI Chair Bracket For wallhung - Pair | Pair | 1422 | 2020-08-31 | 1900-01-01 | 8 | 8 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC Brass Elbow 1/2" | Nos. | 1423 | 2020-08-31 | 1900-01-01 | 64 | 64 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC Brass Elbow 1/2" | Nos. | 1424 | 2020-08-31 | 1900-01-01 | 64 | 64 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC Elbow 1/2" | Nos. | 1425 | 2020-08-31 | 1900-01-01 | 100 | 100 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC Elbow 1/2" | Nos. | 1426 | 2020-08-31 | 1900-01-01 | 108 | 108 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC Elbow 11/4" | Nos. | 1427 | 2020-08-31 | 1900-01-01 | 16 | 16 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC Elbow 11/4" | Nos. | 1428 | 2020-08-31 | 1900-01-01 | 64 | 64 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC End Cap 1/2" | Nos. | 1429 | 2020-08-31 | 1900-01-01 | 20 | 20 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC End Cap 1/2" | Nos. | 1430 | 2020-08-31 | 1900-01-01 | 20 | 20 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC End Cap 11/4" | Nos. | 1431 | 2020-08-31 | 1900-01-01 | 8 | 8 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC End Cap 11/4" | Nos. | 1432 | 2020-08-31 | 1900-01-01 | 8 | 8 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC End Plug 1/2" | Nos. | 1433 | 2020-08-31 | 1900-01-01 | 64 | 64 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC End Plug 1/2" | Nos. | 1434 | 2020-08-31 | 1900-01-01 | 64 | 64 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC FTA Brass 11/4" | Nos. | 1435 | 2020-08-31 | 1900-01-01 | 8 | 8 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC FTA Brass 11/4" | Nos. | 1436 | 2020-08-31 | 1900-01-01 | 8 | 8 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC MTA Brass 1/2" | Nos. | 1437 | 2020-08-31 | 1900-01-01 | 32 | 32 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC MTA Brass 1/2" | Nos. | 1438 | 2020-08-31 | 1900-01-01 | 32 | 32 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC MTA Brass 11/4" | Nos. | 1439 | 2020-08-31 | 1900-01-01 | 8 | 8 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC MTA Brass 11/4" | Nos. | 1440 | 2020-08-31 | 1900-01-01 | 8 | 8 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC Pipe 1/2" SDR-11 (3 Mtr.) | Nos. | 1441 | 2020-08-31 | 1900-01-01 | 34 | 34 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC Pipe 1/2" SDR-11 (3 Mtr.) | Nos. | 1442 | 2020-08-31 | 1900-01-01 | 30.8 | 30.8 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC Pipe11/4" SDR-11 (3 Mtr.) | Nos. | 1443 | 2020-08-31 | 1900-01-01 | 4 | 4 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC Pipe11/4" SDR-11 (3 Mtr.) | Nos. | 1444 | 2020-08-31 | 1900-01-01 | 8.8 | 8.8 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC Solvent Soilibond 1000ml. - Tin. | Tin | 1445 | 2020-08-31 | 1900-01-01 | 0.6 | 0.6 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC Solvent Soilibond 1000ml. - Tin. | Tin | 1446 | 2020-08-31 | 1900-01-01 | 6 | 6 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC Tee 1/2" | Nos. | 1447 | 2020-08-31 | 1900-01-01 | 32 | 32 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC Tee 1/2" | Nos. | 1448 | 2020-08-31 | 1900-01-01 | 40 | 40 | 0 | Rakesh Shinde | Completed
41 Estera | Flush valve Consiled 1 1/4" Brass (Jaquar) | Nos. | 1449 | 2020-08-31 | 1900-01-01 | 8 | 8 | 0 | Rakesh Shinde | Completed
41 Estera | Flush valve Consiled 1 1/4" Brass (Jaquar) | Nos. | 1450 | 2020-08-31 | 1900-01-01 | 8 | 8 | 0 | Rakesh Shinde | Completed
41 Estera | Hold Tite 500 gm | Tin | 1451 | 2020-08-31 | 1900-01-01 | 1.2 | 1.2 | 0 | Rakesh Shinde | Completed
41 Estera | Multi Floor trap | No. | 1452 | 2020-08-31 | 1900-01-01 | 12 | 12 | 0 | Rakesh Shinde | Completed
41 Estera | Multi Floor trap | No. | 1453 | 2020-08-31 | 1900-01-01 | 16 | 16 | 0 | Rakesh Shinde | Completed
41 Estera | Nails Plumbing 2" | Kg | 1454 | 2020-08-31 | 1900-01-01 | 4 | 4 | 0 | Rakesh Shinde | Completed
41 Estera | Nails Plumbing 2" | Kg | 1455 | 2020-08-31 | 1900-01-01 | 4 | 4 | 0 | Rakesh Shinde | Completed
41 Estera | Pipe Agri. 2" x 20' - 6 kgs. | NO | 1456 | 2020-08-31 | 1900-01-01 | 1.8 | 1.8 | 0 | Rakesh Shinde | Completed
41 Estera | Pipe Agri. 2" x 20' - 6 kgs. | NO | 1457 | 2020-08-31 | 1900-01-01 | 4 | 4 | 0 | Rakesh Shinde | Completed
41 Estera | Pipe Agri. 3" x 20' - 4 kgs. | NO | 1458 | 2020-08-31 | 1900-01-01 | 6.48 | 6.48 | 0 | Rakesh Shinde | Completed
41 Estera | Pipe Agri. 3" x 20' - 4 kgs. | NO | 1459 | 2020-08-31 | 1900-01-01 | 8.8 | 8.8 | 0 | Rakesh Shinde | Completed
41 Estera | PVC Agri Bushing 50mm x 40mm - 10 Kgs | Nos | 1460 | 2020-08-31 | 1900-01-01 | 16 | 16 | 0 | Rakesh Shinde | Completed
41 Estera | PVC Agri Bushing 50mm x 40mm - 10 Kgs | Nos | 1461 | 2020-08-31 | 1900-01-01 | 12 | 12 | 0 | Rakesh Shinde | Completed
41 Estera | PVC Agri Elbow 40mm - 10 kgs | NO | 1462 | 2020-08-31 | 1900-01-01 | 8 | 8 | 0 | Rakesh Shinde | Completed
41 Estera | PVC Agri Elbow 50mm - 10 kgs | NO | 1463 | 2020-08-31 | 1900-01-01 | 4 | 4 | 0 | Rakesh Shinde | Completed
41 Estera | PVC Agri Elbow 50mm - 10 kgs | NO | 1464 | 2020-08-31 | 1900-01-01 | 4 | 4 | 0 | Rakesh Shinde | Completed
41 Estera | PVC Agri End Cap 40 mm - 10 kgs | NO | 1465 | 2020-08-31 | 1900-01-01 | 16 | 16 | 0 | Rakesh Shinde | Completed
41 Estera | PVC Agri End Cap 40 mm - 10 kgs | NO | 1466 | 2020-08-31 | 1900-01-01 | 16 | 16 | 0 | Rakesh Shinde | Completed
41 Estera | PVC Agri End Cap 50 mm - 10 kgs | NO | 1467 | 2020-08-31 | 1900-01-01 | 4 | 4 | 0 | Rakesh Shinde | Completed
41 Estera | PVC Agri End Cap 50 mm - 10 kgs | NO | 1468 | 2020-08-31 | 1900-01-01 | 12 | 12 | 0 | Rakesh Shinde | Completed
41 Estera | PVC Agri Plain Long Bend 40mm - 10 kgs | No. | 1469 | 2020-08-31 | 1900-01-01 | 8 | 8 | 0 | Rakesh Shinde | Completed
41 Estera | PVC Agri Plain Long Bend 40mm - 10 kgs | No. | 1470 | 2020-08-31 | 1900-01-01 | 12 | 12 | 0 | Rakesh Shinde | Completed
41 Estera | PVC Agri Plain Tee 75mm 4 Kg. | No. | 1471 | 2020-08-31 | 1900-01-01 | 4 | 4 | 0 | Rakesh Shinde | Completed
41 Estera | PVC Agri Plain Tee 75mm 4 Kg. | No. | 1472 | 2020-08-31 | 1900-01-01 | 4 | 4 | 0 | Rakesh Shinde | Completed
41 Estera | 065 Divertor - 40mm Carterage | Nos. | 1473 | 2020-08-31 | 1900-01-01 | 6 | 6 | 0 | Rakesh Shinde | Completed
41 Estera | 065 Divertor - 40mm Carterage | Nos. | 1474 | 2020-08-31 | 1900-01-01 | 6 | 6 | 0 | Rakesh Shinde | Completed
41 Estera | ACO- Nahani Trap Quadrato | Nos | 1475 | 2020-08-31 | 1900-01-01 | 4 | 0 | 0 | Rakesh Shinde | Unapproved
41 Estera | ACO- Nahani Trap Quadrato | Nos | 1476 | 2020-08-31 | 1900-01-01 | 4 | 0 | 0 | Rakesh Shinde | Unapproved
41 Estera | Agri. PVC Elbow 110mm. H/W | NO | 1477 | 2020-08-31 | 1900-01-01 | 12 | 12 | 0 | Rakesh Shinde | Completed
41 Estera | CI Chair Bracket For wallhung - Pair | Pair | 1478 | 2020-08-31 | 1900-01-01 | 6 | 6 | 0 | Rakesh Shinde | Completed
41 Estera | CI Chair Bracket For wallhung - Pair | Pair | 1479 | 2020-08-31 | 1900-01-01 | 6 | 6 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC Brass Elbow 1/2" | Nos. | 1480 | 2020-08-31 | 1900-01-01 | 48 | 48 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC Brass Elbow 1/2" | Nos. | 1481 | 2020-08-31 | 1900-01-01 | 48 | 48 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC Elbow 1/2" | Nos. | 1482 | 2020-08-31 | 1900-01-01 | 81 | 81 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC Elbow 1/2" | Nos. | 1483 | 2020-08-31 | 1900-01-01 | 75 | 75 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC Elbow 11/4" | Nos. | 1484 | 2020-08-31 | 1900-01-01 | 48 | 48 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC Elbow 11/4" | Nos. | 1485 | 2020-08-31 | 1900-01-01 | 12 | 12 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC End Cap 1/2" | Nos. | 1486 | 2020-08-31 | 1900-01-01 | 15 | 15 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC End Cap 1/2" | Nos. | 1487 | 2020-08-31 | 1900-01-01 | 15 | 15 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC End Cap 11/4" | Nos. | 1488 | 2020-08-31 | 1900-01-01 | 6 | 6 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC End Cap 11/4" | Nos. | 1489 | 2020-08-31 | 1900-01-01 | 6 | 6 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC End Plug 1/2" | Nos. | 1490 | 2020-08-31 | 1900-01-01 | 48 | 48 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC End Plug 1/2" | Nos. | 1491 | 2020-08-31 | 1900-01-01 | 48 | 48 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC FTA Brass 11/4" | Nos. | 1492 | 2020-08-31 | 1900-01-01 | 6 | 6 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC FTA Brass 11/4" | Nos. | 1493 | 2020-08-31 | 1900-01-01 | 6 | 6 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC MTA Brass 1/2" | Nos. | 1494 | 2020-08-31 | 1900-01-01 | 24 | 24 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC MTA Brass 1/2" | Nos. | 1495 | 2020-08-31 | 1900-01-01 | 24 | 24 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC MTA Brass 11/4" | Nos. | 1496 | 2020-08-31 | 1900-01-01 | 6 | 6 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC MTA Brass 11/4" | Nos. | 1497 | 2020-08-31 | 1900-01-01 | 6 | 6 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC Pipe 1/2" SDR-11 (3 Mtr.) | Nos. | 1498 | 2020-08-31 | 1900-01-01 | 25.5 | 25.5 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC Pipe 1/2" SDR-11 (3 Mtr.) | Nos. | 1499 | 2020-08-31 | 1900-01-01 | 23.1 | 23.1 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC Pipe11/4" SDR-11 (3 Mtr.) | Nos. | 1500 | 2020-08-31 | 1900-01-01 | 6.6 | 6.6 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC Pipe11/4" SDR-11 (3 Mtr.) | Nos. | 1501 | 2020-08-31 | 1900-01-01 | 3 | 3 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC Solvent Soilibond 1000ml. - Tin. | Tin | 1502 | 2020-08-31 | 1900-01-01 | 0.45 | 0.45 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC Solvent Soilibond 1000ml. - Tin. | Tin | 1503 | 2020-08-31 | 1900-01-01 | 4.5 | 4.5 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC Tee 1/2" | Nos. | 1504 | 2020-08-31 | 1900-01-01 | 30 | 30 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC Tee 1/2" | Nos. | 1505 | 2020-08-31 | 1900-01-01 | 24 | 24 | 0 | Rakesh Shinde | Completed
41 Estera | Flush valve Consiled 1 1/4" Brass (Jaquar) | Nos. | 1506 | 2020-08-31 | 1900-01-01 | 6 | 6 | 0 | Rakesh Shinde | Completed
41 Estera | Flush valve Consiled 1 1/4" Brass (Jaquar) | Nos. | 1507 | 2020-08-31 | 1900-01-01 | 6 | 6 | 0 | Rakesh Shinde | Completed
41 Estera | Hold Tite 500 gm | Tin | 1508 | 2020-08-31 | 1900-01-01 | 0.9 | 0.9 | 0 | Rakesh Shinde | Completed
41 Estera | Multi Floor trap | No. | 1509 | 2020-08-31 | 1900-01-01 | 12 | 12 | 0 | Rakesh Shinde | Completed
41 Estera | Multi Floor trap | No. | 1510 | 2020-08-31 | 1900-01-01 | 9 | 9 | 0 | Rakesh Shinde | Completed
41 Estera | Nails Plumbing 2" | Kg | 1511 | 2020-08-31 | 1900-01-01 | 3 | 3 | 0 | Rakesh Shinde | Completed
41 Estera | Nails Plumbing 2" | Kg | 1512 | 2020-08-31 | 1900-01-01 | 3 | 3 | 0 | Rakesh Shinde | Completed
41 Estera | Pipe Agri. 2" x 20' - 6 kgs. | NO | 1513 | 2020-08-31 | 1900-01-01 | 1.35 | 1.35 | 0 | Rakesh Shinde | Completed
41 Estera | Pipe Agri. 2" x 20' - 6 kgs. | NO | 1514 | 2020-08-31 | 1900-01-01 | 3 | 3 | 0 | Rakesh Shinde | Completed
41 Estera | Pipe Agri. 3" x 20' - 4 kgs. | NO | 1515 | 2020-08-31 | 1900-01-01 | 4.86 | 4.86 | 0 | Rakesh Shinde | Completed
41 Estera | Pipe Agri. 3" x 20' - 4 kgs. | NO | 1516 | 2020-08-31 | 1900-01-01 | 6.6 | 6.6 | 0 | Rakesh Shinde | Completed
41 Estera | PVC Agri Bushing 50mm x 40mm - 10 Kgs | Nos | 1517 | 2020-08-31 | 1900-01-01 | 9 | 9 | 0 | Rakesh Shinde | Completed
41 Estera | PVC Agri Bushing 50mm x 40mm - 10 Kgs | Nos | 1518 | 2020-08-31 | 1900-01-01 | 12 | 12 | 0 | Rakesh Shinde | Completed
41 Estera | PVC Agri Elbow 40mm - 10 kgs | NO | 1519 | 2020-08-31 | 1900-01-01 | 6 | 6 | 0 | Rakesh Shinde | Completed
41 Estera | PVC Agri Elbow 50mm - 10 kgs | NO | 1520 | 2020-08-31 | 1900-01-01 | 3 | 3 | 0 | Rakesh Shinde | Completed
41 Estera | PVC Agri Elbow 50mm - 10 kgs | NO | 1521 | 2020-08-31 | 1900-01-01 | 3 | 3 | 0 | Rakesh Shinde | Completed
41 Estera | PVC Agri End Cap 40 mm - 10 kgs | NO | 1522 | 2020-08-31 | 1900-01-01 | 12 | 12 | 0 | Rakesh Shinde | Completed
41 Estera | PVC Agri End Cap 40 mm - 10 kgs | NO | 1523 | 2020-08-31 | 1900-01-01 | 12 | 12 | 0 | Rakesh Shinde | Completed
41 Estera | PVC Agri End Cap 50 mm - 10 kgs | NO | 1524 | 2020-08-31 | 1900-01-01 | 9 | 9 | 0 | Rakesh Shinde | Completed
41 Estera | PVC Agri End Cap 50 mm - 10 kgs | NO | 1525 | 2020-08-31 | 1900-01-01 | 3 | 3 | 0 | Rakesh Shinde | Completed
41 Estera | PVC Agri Plain Long Bend 40mm - 10 kgs | No. | 1526 | 2020-08-31 | 1900-01-01 | 9 | 9 | 0 | Rakesh Shinde | Completed
41 Estera | PVC Agri Plain Long Bend 40mm - 10 kgs | No. | 1527 | 2020-08-31 | 1900-01-01 | 6 | 6 | 0 | Rakesh Shinde | Completed
41 Estera | PVC Agri Plain Tee 75mm 4 Kg. | No. | 1528 | 2020-08-31 | 1900-01-01 | 3 | 3 | 0 | Rakesh Shinde | Completed
41 Estera | PVC Agri Plain Tee 75mm 4 Kg. | No. | 1529 | 2020-08-31 | 1900-01-01 | 3 | 3 | 0 | Rakesh Shinde | Completed
41 Estera | 065 Divertor - 40mm Carterage | Nos. | 1530 | 2020-08-31 | 1900-01-01 | 8 | 8 | 0 | Rakesh Shinde | Completed
41 Estera | 065 Divertor - 40mm Carterage | Nos. | 1531 | 2020-08-31 | 1900-01-01 | 8 | 8 | 0 | Rakesh Shinde | Completed
41 Estera | ACO- Nahani Trap Quadrato | Nos | 1532 | 2020-08-31 | 1900-01-01 | 4 | 4 | 0 | Rakesh Shinde | Completed
41 Estera | ACO- Nahani Trap Quadrato | Nos | 1533 | 2020-08-31 | 1900-01-01 | 4 | 4 | 0 | Rakesh Shinde | Completed
41 Estera | Agri. PVC Elbow 110mm. H/W | NO | 1534 | 2020-08-31 | 1900-01-01 | 16 | 16 | 0 | Rakesh Shinde | Completed
41 Estera | CI Chair Bracket For wallhung - Pair | Pair | 1535 | 2020-08-31 | 1900-01-01 | 8 | 8 | 0 | Rakesh Shinde | Completed
41 Estera | CI Chair Bracket For wallhung - Pair | Pair | 1536 | 2020-08-31 | 1900-01-01 | 8 | 8 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC Brass Elbow 1/2" | Nos. | 1537 | 2020-08-31 | 1900-01-01 | 64 | 64 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC Brass Elbow 1/2" | Nos. | 1538 | 2020-08-31 | 1900-01-01 | 64 | 64 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC Elbow 1/2" | Nos. | 1539 | 2020-08-31 | 1900-01-01 | 108 | 108 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC Elbow 1/2" | Nos. | 1540 | 2020-08-31 | 1900-01-01 | 100 | 100 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC Elbow 11/4" | Nos. | 1541 | 2020-08-31 | 1900-01-01 | 64 | 64 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC Elbow 11/4" | Nos. | 1542 | 2020-08-31 | 1900-01-01 | 16 | 16 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC End Cap 1/2" | Nos. | 1543 | 2020-08-31 | 1900-01-01 | 20 | 20 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC End Cap 1/2" | Nos. | 1544 | 2020-08-31 | 1900-01-01 | 20 | 20 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC End Cap 11/4" | Nos. | 1545 | 2020-08-31 | 1900-01-01 | 8 | 8 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC End Cap 11/4" | Nos. | 1546 | 2020-08-31 | 1900-01-01 | 8 | 8 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC End Plug 1/2" | Nos. | 1547 | 2020-08-31 | 1900-01-01 | 64 | 64 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC End Plug 1/2" | Nos. | 1548 | 2020-08-31 | 1900-01-01 | 64 | 64 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC FTA Brass 11/4" | Nos. | 1549 | 2020-08-31 | 1900-01-01 | 8 | 8 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC FTA Brass 11/4" | Nos. | 1550 | 2020-08-31 | 1900-01-01 | 8 | 8 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC MTA Brass 1/2" | Nos. | 1551 | 2020-08-31 | 1900-01-01 | 32 | 32 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC MTA Brass 1/2" | Nos. | 1552 | 2020-08-31 | 1900-01-01 | 32 | 32 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC MTA Brass 11/4" | Nos. | 1553 | 2020-08-31 | 1900-01-01 | 8 | 8 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC MTA Brass 11/4" | Nos. | 1554 | 2020-08-31 | 1900-01-01 | 8 | 8 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC Pipe 1/2" SDR-11 (3 Mtr.) | Nos. | 1555 | 2020-08-31 | 1900-01-01 | 34 | 34 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC Pipe 1/2" SDR-11 (3 Mtr.) | Nos. | 1556 | 2020-08-31 | 1900-01-01 | 30.8 | 30.8 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC Pipe11/4" SDR-11 (3 Mtr.) | Nos. | 1557 | 2020-08-31 | 1900-01-01 | 8.8 | 8.8 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC Pipe11/4" SDR-11 (3 Mtr.) | Nos. | 1558 | 2020-08-31 | 1900-01-01 | 4 | 4 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC Solvent Soilibond 1000ml. - Tin. | Tin | 1559 | 2020-08-31 | 1900-01-01 | 0.6 | 0.6 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC Solvent Soilibond 1000ml. - Tin. | Tin | 1560 | 2020-08-31 | 1900-01-01 | 6 | 6 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC Tee 1/2" | Nos. | 1561 | 2020-08-31 | 1900-01-01 | 40 | 40 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC Tee 1/2" | Nos. | 1562 | 2020-08-31 | 1900-01-01 | 32 | 32 | 0 | Rakesh Shinde | Completed
41 Estera | Flush valve Consiled 1 1/4" Brass (Jaquar) | Nos. | 1563 | 2020-08-31 | 1900-01-01 | 8 | 8 | 0 | Rakesh Shinde | Completed
41 Estera | Flush valve Consiled 1 1/4" Brass (Jaquar) | Nos. | 1564 | 2020-08-31 | 1900-01-01 | 8 | 8 | 0 | Rakesh Shinde | Completed
41 Estera | Hold Tite 500 gm | Tin | 1565 | 2020-08-31 | 1900-01-01 | 1.2 | 1.2 | 0 | Rakesh Shinde | Completed
41 Estera | Multi Floor trap | No. | 1566 | 2020-08-31 | 1900-01-01 | 16 | 16 | 0 | Rakesh Shinde | Completed
41 Estera | Multi Floor trap | No. | 1567 | 2020-08-31 | 1900-01-01 | 12 | 12 | 0 | Rakesh Shinde | Completed
41 Estera | Nails Plumbing 2" | Kg | 1568 | 2020-08-31 | 1900-01-01 | 4 | 4 | 0 | Rakesh Shinde | Completed
41 Estera | Nails Plumbing 2" | Kg | 1569 | 2020-08-31 | 1900-01-01 | 4 | 4 | 0 | Rakesh Shinde | Completed
41 Estera | Pipe Agri. 2" x 20' - 6 kgs. | NO | 1570 | 2020-08-31 | 1900-01-01 | 1.8 | 1.8 | 0 | Rakesh Shinde | Completed
41 Estera | Pipe Agri. 2" x 20' - 6 kgs. | NO | 1571 | 2020-08-31 | 1900-01-01 | 4 | 4 | 0 | Rakesh Shinde | Completed
41 Estera | Pipe Agri. 3" x 20' - 4 kgs. | NO | 1572 | 2020-08-31 | 1900-01-01 | 6.48 | 6.48 | 0 | Rakesh Shinde | Completed
41 Estera | Pipe Agri. 3" x 20' - 4 kgs. | NO | 1573 | 2020-08-31 | 1900-01-01 | 8.8 | 8.8 | 0 | Rakesh Shinde | Completed
41 Estera | PVC Agri Bushing 50mm x 40mm - 10 Kgs | Nos | 1574 | 2020-08-31 | 1900-01-01 | 12 | 12 | 0 | Rakesh Shinde | Completed
41 Estera | PVC Agri Bushing 50mm x 40mm - 10 Kgs | Nos | 1575 | 2020-08-31 | 1900-01-01 | 16 | 16 | 0 | Rakesh Shinde | Completed
41 Estera | PVC Agri Elbow 40mm - 10 kgs | NO | 1576 | 2020-08-31 | 1900-01-01 | 8 | 8 | 0 | Rakesh Shinde | Completed
41 Estera | PVC Agri Elbow 50mm - 10 kgs | NO | 1577 | 2020-08-31 | 1900-01-01 | 4 | 4 | 0 | Rakesh Shinde | Completed
41 Estera | PVC Agri Elbow 50mm - 10 kgs | NO | 1578 | 2020-08-31 | 1900-01-01 | 4 | 4 | 0 | Rakesh Shinde | Completed
41 Estera | PVC Agri End Cap 40 mm - 10 kgs | NO | 1579 | 2020-08-31 | 1900-01-01 | 16 | 16 | 0 | Rakesh Shinde | Completed
41 Estera | PVC Agri End Cap 40 mm - 10 kgs | NO | 1580 | 2020-08-31 | 1900-01-01 | 16 | 16 | 0 | Rakesh Shinde | Completed
41 Estera | PVC Agri End Cap 50 mm - 10 kgs | NO | 1581 | 2020-08-31 | 1900-01-01 | 12 | 12 | 0 | Rakesh Shinde | Completed
41 Estera | PVC Agri End Cap 50 mm - 10 kgs | NO | 1582 | 2020-08-31 | 1900-01-01 | 4 | 4 | 0 | Rakesh Shinde | Completed
41 Estera | PVC Agri Plain Long Bend 40mm - 10 kgs | No. | 1583 | 2020-08-31 | 1900-01-01 | 12 | 12 | 0 | Rakesh Shinde | Completed
41 Estera | PVC Agri Plain Long Bend 40mm - 10 kgs | No. | 1584 | 2020-08-31 | 1900-01-01 | 8 | 8 | 0 | Rakesh Shinde | Completed
41 Estera | PVC Agri Plain Tee 75mm 4 Kg. | No. | 1585 | 2020-08-31 | 1900-01-01 | 4 | 4 | 0 | Rakesh Shinde | Completed
41 Estera | PVC Agri Plain Tee 75mm 4 Kg. | No. | 1586 | 2020-08-31 | 1900-01-01 | 4 | 4 | 0 | Rakesh Shinde | Completed
41 Estera | 065 Divertor - 40mm Carterage | Nos. | 1587 | 2020-08-31 | 1900-01-01 | 8 | 8 | 0 | Rakesh Shinde | Completed
41 Estera | 065 Divertor - 40mm Carterage | Nos. | 1588 | 2020-08-31 | 1900-01-01 | 8 | 8 | 0 | Rakesh Shinde | Completed
41 Estera | ACO- Nahani Trap Quadrato | Nos | 1589 | 2020-08-31 | 1900-01-01 | 4 | 4 | 0 | Rakesh Shinde | Completed
41 Estera | ACO- Nahani Trap Quadrato | Nos | 1590 | 2020-08-31 | 1900-01-01 | 4 | 4 | 0 | Rakesh Shinde | Completed
41 Estera | Agri. PVC Elbow 110mm. H/W | NO | 1591 | 2020-08-31 | 1900-01-01 | 16 | 16 | 0 | Rakesh Shinde | Completed
41 Estera | CI Chair Bracket For wallhung - Pair | Pair | 1592 | 2020-08-31 | 1900-01-01 | 8 | 8 | 0 | Rakesh Shinde | Completed
41 Estera | CI Chair Bracket For wallhung - Pair | Pair | 1593 | 2020-08-31 | 1900-01-01 | 8 | 8 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC Brass Elbow 1/2" | Nos. | 1594 | 2020-08-31 | 1900-01-01 | 64 | 64 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC Brass Elbow 1/2" | Nos. | 1595 | 2020-08-31 | 1900-01-01 | 64 | 64 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC Elbow 1/2" | Nos. | 1596 | 2020-08-31 | 1900-01-01 | 108 | 108 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC Elbow 1/2" | Nos. | 1597 | 2020-08-31 | 1900-01-01 | 100 | 100 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC Elbow 11/4" | Nos. | 1598 | 2020-08-31 | 1900-01-01 | 64 | 64 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC Elbow 11/4" | Nos. | 1599 | 2020-08-31 | 1900-01-01 | 16 | 16 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC End Cap 1/2" | Nos. | 1600 | 2020-08-31 | 1900-01-01 | 20 | 20 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC End Cap 1/2" | Nos. | 1601 | 2020-08-31 | 1900-01-01 | 20 | 20 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC End Cap 11/4" | Nos. | 1602 | 2020-08-31 | 1900-01-01 | 8 | 8 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC End Cap 11/4" | Nos. | 1603 | 2020-08-31 | 1900-01-01 | 8 | 8 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC End Plug 1/2" | Nos. | 1604 | 2020-08-31 | 1900-01-01 | 64 | 64 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC End Plug 1/2" | Nos. | 1605 | 2020-08-31 | 1900-01-01 | 64 | 64 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC FTA Brass 11/4" | Nos. | 1606 | 2020-08-31 | 1900-01-01 | 8 | 8 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC FTA Brass 11/4" | Nos. | 1607 | 2020-08-31 | 1900-01-01 | 8 | 8 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC MTA Brass 1/2" | Nos. | 1608 | 2020-08-31 | 1900-01-01 | 32 | 32 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC MTA Brass 1/2" | Nos. | 1609 | 2020-08-31 | 1900-01-01 | 32 | 32 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC MTA Brass 11/4" | Nos. | 1610 | 2020-08-31 | 1900-01-01 | 8 | 8 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC MTA Brass 11/4" | Nos. | 1611 | 2020-08-31 | 1900-01-01 | 8 | 8 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC Pipe 1/2" SDR-11 (3 Mtr.) | Nos. | 1612 | 2020-08-31 | 1900-01-01 | 34 | 34 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC Pipe 1/2" SDR-11 (3 Mtr.) | Nos. | 1613 | 2020-08-31 | 1900-01-01 | 30.8 | 30.8 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC Pipe11/4" SDR-11 (3 Mtr.) | Nos. | 1614 | 2020-08-31 | 1900-01-01 | 8.8 | 8.8 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC Pipe11/4" SDR-11 (3 Mtr.) | Nos. | 1615 | 2020-08-31 | 1900-01-01 | 4 | 4 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC Solvent Soilibond 1000ml. - Tin. | Tin | 1616 | 2020-08-31 | 1900-01-01 | 0.6 | 0.6 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC Solvent Soilibond 1000ml. - Tin. | Tin | 1617 | 2020-08-31 | 1900-01-01 | 6 | 6 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC Tee 1/2" | Nos. | 1618 | 2020-08-31 | 1900-01-01 | 40 | 40 | 0 | Rakesh Shinde | Completed
41 Estera | CPVC Tee 1/2" | Nos. | 1619 | 2020-08-31 | 1900-01-01 | 32 | 32 | 0 | Rakesh Shinde | Completed
41 Estera | Flush valve Consiled 1 1/4" Brass (Jaquar) | Nos. | 1620 | 2020-08-31 | 1900-01-01 | 8 | 8 | 0 | Rakesh Shinde | Completed
41 Estera | Flush valve Consiled 1 1/4" Brass (Jaquar) | Nos. | 1621 | 2020-08-31 | 1900-01-01 | 8 | 8 | 0 | Rakesh Shinde | Completed
41 Estera | Hold Tite 500 gm | Tin | 1622 | 2020-08-31 | 1900-01-01 | 1.2 | 1.2 | 0 | Rakesh Shinde | Completed
41 Estera | Multi Floor trap | No. | 1623 | 2020-08-31 | 1900-01-01 | 16 | 16 | 0 | Rakesh Shinde | Completed
41 Estera | Multi Floor trap | No. | 1624 | 2020-08-31 | 1900-01-01 | 12 | 12 | 0 | Rakesh Shinde | Completed
41 Estera | Nails Plumbing 2" | Kg | 1625 | 2020-08-31 | 1900-01-01 | 4 | 4 | 0 | Rakesh Shinde | Completed
41 Estera | Nails Plumbing 2" | Kg | 1626 | 2020-08-31 | 1900-01-01 | 4 | 4 | 0 | Rakesh Shinde | Completed
41 Estera | Pipe Agri. 2" x 20' - 6 kgs. | NO | 1627 | 2020-08-31 | 1900-01-01 | 1.8 | 1.8 | 0 | Rakesh Shinde | Completed
41 Estera | Pipe Agri. 2" x 20' - 6 kgs. | NO | 1628 | 2020-08-31 | 1900-01-01 | 4 | 4 | 0 | Rakesh Shinde | Completed
41 Estera | Pipe Agri. 3" x 20' - 4 kgs. | NO | 1629 | 2020-08-31 | 1900-01-01 | 6.48 | 6.48 | 0 | Rakesh Shinde | Completed
41 Estera | Pipe Agri. 3" x 20' - 4 kgs. | NO | 1630 | 2020-08-31 | 1900-01-01 | 8.8 | 8.8 | 0 | Rakesh Shinde | Completed
41 Estera | PVC Agri Bushing 50mm x 40mm - 10 Kgs | Nos | 1631 | 2020-08-31 | 1900-01-01 | 12 | 12 | 0 | Rakesh Shinde | Completed
41 Estera | PVC Agri Bushing 50mm x 40mm - 10 Kgs | Nos | 1632 | 2020-08-31 | 1900-01-01 | 16 | 16 | 0 | Rakesh Shinde | Completed
41 Estera | PVC Agri Elbow 40mm - 10 kgs | NO | 1633 | 2020-08-31 | 1900-01-01 | 8 | 8 | 0 | Rakesh Shinde | Completed
41 Estera | PVC Agri Elbow 50mm - 10 kgs | NO | 1634 | 2020-08-31 | 1900-01-01 | 4 | 4 | 0 | Rakesh Shinde | Completed
41 Estera | PVC Agri Elbow 50mm - 10 kgs | NO | 1635 | 2020-08-31 | 1900-01-01 | 4 | 4 | 0 | Rakesh Shinde | Completed
41 Estera | PVC Agri End Cap 40 mm - 10 kgs | NO | 1636 | 2020-08-31 | 1900-01-01 | 16 | 16 | 0 | Rakesh Shinde | Completed
41 Estera | PVC Agri End Cap 40 mm - 10 kgs | NO | 1637 | 2020-08-31 | 1900-01-01 | 16 | 16 | 0 | Rakesh Shinde | Completed
41 Estera | PVC Agri End Cap 50 mm - 10 kgs | NO | 1638 | 2020-08-31 | 1900-01-01 | 12 | 12 | 0 | Rakesh Shinde | Completed
41 Estera | PVC Agri End Cap 50 mm - 10 kgs | NO | 1639 | 2020-08-31 | 1900-01-01 | 4 | 4 | 0 | Rakesh Shinde | Completed
41 Estera | PVC Agri Plain Long Bend 40mm - 10 kgs | No. | 1640 | 2020-08-31 | 1900-01-01 | 12 | 12 | 0 | Rakesh Shinde | Completed
41 Estera | PVC Agri Plain Long Bend 40mm - 10 kgs | No. | 1641 | 2020-08-31 | 1900-01-01 | 8 | 8 | 0 | Rakesh Shinde | Completed
41 Estera | PVC Agri Plain Tee 75mm 4 Kg. | No. | 1642 | 2020-08-31 | 1900-01-01 | 4 | 4 | 0 | Rakesh Shinde | Completed
41 Estera | PVC Agri Plain Tee 75mm 4 Kg. | No. | 1643 | 2020-08-31 | 1900-01-01 | 4 | 4 | 0 | Rakesh Shinde | Completed