## Task Details638270889799062718_
Task Details
Project Name : GOODWILL VERVE
Task Name : All
Total Records: 1353 Records 1 to 1353
Page 1 of 1
Task (1) | Qty (2) | Unit (3) | Planned Start (4) | Planned Finish (5) | Actual Start (6) | Actual Finish (7) | Planned Duration (8)=(4)-(5) Days | Actual Duration (9)=(6)-(7) Days | Start Variance (10)=(4)-(6) Days | Finish Variance (11)=(4)-(5) Days | Remark
GOODWILL VERVE | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
A- BUILDING | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
SUBSTRUCTURE | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
EARTHWORK | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Earthwork - Excavation in hard rock | 3732.2 | Cu.Mtrs | 27 Aug 2022 |  | 04 May 2023 |  | 0 | 0 | 250 | 0
Earthwork - Excavation in soft rock | 2124.63 | Cu.Mtrs | 27 Aug 2022 |  | 04 May 2023 |  | 0 | 0 | 250 | 0
RCC WORK | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
RCC WORK R - RCC (M25) | 0 | Cu.Mtr | 27 Aug 2022 |  | 12 Sep 2022 |  | 0 | 0 | 16 | 0
RCC WORK R - PCC 1:2:4 (M15) | 250 | Cu.Mtr | 27 Aug 2022 |  | 01 Oct 2022 |  | 0 | 0 | 35 | 0
RCC WORK R - RCC (M25) | 0 | Cu.Mtr | 27 Aug 2022 |  | 01 Oct 2022 |  | 0 | 0 | 35 | 0
RCC WORK R - RCC (M25) | 0 | Cu.Mtr | 27 Aug 2022 |  | 01 Oct 2022 |  | 0 | 0 | 35 | 0
RCC WORK R - RCC (M25) | 0 | Cu.Mtr | 27 Aug 2022 |  | 01 Oct 2022 |  | 0 | 0 | 35 | 0
RCC WORK RCC Work-M15 | 60 | Cu.Mtr | 27 Aug 2022 |  | 01 Oct 2022 |  | 0 | 0 | 35 | 0
RCC WORK Trimix Work | 174.865 | Cu.Mtr | 27 Aug 2022 |  | 01 Oct 2022 |  | 0 | 0 | 35 | 0
RCC WORK RCC WORK (M30) | 25.109 | Cu.Mtr | 27 Aug 2022 |  | 01 Oct 2022 |  | 0 | 0 | 35 | 0
RCC Work- UGWT (Labour) | 0 | Sq.Ft | 27 Aug 2022 |  | 12 Nov 2022 |  | 0 | 0 | 77 | 0
WATERPROOFING WORK | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Basement Floor-Membrane Waterproofing (Labour) | 0 | Sq.Ft | 27 Aug 2022 |  | 10 Sep 2022 | 28 Jul 2023 | 0 | 321 | 14 | 45133
Basement Floor- Membrane Waterproofing (Material) | 465.0909 | Sq.Ft | 27 Aug 2022 |  |  | 28 Jul 2023 | 0 | 45133 | 0 | 45133
MASONRY WORK | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Basement Floor - Material For 5" AAC Block Brickwork | 4.43 | Cu.Mtrs | 27 Aug 2022 |  | 10 Mar 2023 |  | 0 | 0 | 195 | 0
Basement Floor - Material For 8" AAC Block Brickwork | 2.6 | Cu.Mtr | 27 Aug 2022 |  | 10 Mar 2023 |  | 0 | 0 | 195 | 0
Basement Floor - Material For DPC & Patli M20 | 1.49 | Cu.Mtr | 27 Aug 2022 |  | 10 Mar 2023 |  | 0 | 0 | 195 | 0
Basement Floor - Material For 9" Fly Ash Brickwork | 0 | Sq.Ft | 27 Aug 2022 |  | 10 Mar 2023 |  | 0 | 0 | 195 | 0
Basement Floor - Labour for Brickwork | 0 | Sq.Ft | 27 Aug 2022 |  | 10 Mar 2023 |  | 0 | 0 | 195 | 0
INTERNAL PLASTER WORK | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Basement Floor - Material For Internal Plaster Work (Tar & S | 543.474 | Sq.Ft | 27 Aug 2022 |  | 01 Jun 2023 |  | 0 | 0 | 278 | 0
Basement Floor - Labour For Plaster Work | 0 | Sq.Ft | 27 Aug 2022 |  | 01 Jun 2023 |  | 0 | 0 | 278 | 0
CORE CUTTING WORK | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Basement Floor- Core Cutting Work | 0 | Job | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
FABRICATION WORK | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Basement Floor- Tank Doors Fabrication Work | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Basement Floor - Trench Fabrication Work | 0 | Job | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
TILING WORK | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Basement Floor - Entrance Lobby Flooring | 279.86 | Sq.Ft | 27 Aug 2022 |  | 20 Jun 2023 |  | 0 | 0 | 297 | 0
INTERNAL PAINTING WORK (L+M) | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Basement Floor- Internal Painting Work (L+M) | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
EXTERNAL PAINTING WORK (L+M) | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Basement Floor - External Painting Work | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
GYPSUM PUNNING WORK (L+M) | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Basement Floor- Gypsum Punning Work (L+M) | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
ELECTRICAL WORK | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Basement Floor- Electrical Work (Material) | 0 | Per Floor | 27 Aug 2022 |  | 10 Feb 2023 |  | 0 | 0 | 167 | 0
CONTRACTOR DEPARTMENT LABOUR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Department Labour- BBM & Plaster Work | 0 | Day | 27 Aug 2022 |  | 01 May 2023 |  | 0 | 0 | 247 | 0
Department Labour- Tiling Work | 0 | Day | 27 Aug 2022 |  | 01 May 2023 |  | 0 | 0 | 247 | 0
Department Labour- Painting Work | 0 | Day | 27 Aug 2022 |  | 01 May 2023 |  | 0 | 0 | 247 | 0
Department Labour- Gypsum/POP Work | 0 | Day | 27 Aug 2022 |  | 01 May 2023 |  | 0 | 0 | 247 | 0
Department Labour- Electrical Work | 0 | Day | 27 Aug 2022 |  | 01 May 2023 |  | 0 | 0 | 247 | 0
Department Labour- Fabrication Work | 0 | Day | 27 Aug 2022 |  | 01 May 2023 |  | 0 | 0 | 247 | 0
Department Labour- Plumbing Work | 0 | Day | 27 Aug 2022 |  | 01 May 2023 |  | 0 | 0 | 247 | 0
SUPERSTRUCTURE | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
RCC WORK | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
GROUND FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
1st to 2nd Slab (1st Fl) - Col & Lift pardi (M40) | 161.46 | Cu.Mtr | 27 Aug 2022 |  | 30 Dec 2022 |  | 0 | 0 | 125 | 0
1st Slab (Ground Fl) - Slab, Beam & staircase (M30) | 418.6 | Cu.Mtr | 27 Aug 2022 |  | 01 Oct 2022 |  | 0 | 0 | 35 | 0
Trimix Work (Ground Fl) | 0 | Cu.Mtr | 27 Aug 2022 |  | 14 Mar 2023 |  | 0 | 0 | 199 | 0
1ST FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
2nd Slab (1st Fl) - Slab, Beam & staircase (M30) | 206.84 | Cu.Mtr | 27 Aug 2022 |  | 04 Jan 2023 |  | 0 | 0 | 130 | 0
2nd to 3rd Slab (1st Fl) - Col & Lift pardi (M40) | 88.32 | Cu.Mtr | 27 Aug 2022 |  | 17 Jan 2023 |  | 0 | 0 | 143 | 0
2ND FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
3rd Slab (2nd Fl) - Slab, Beam & staircase (M30) | 211.71 | Cu.Mtr | 27 Aug 2022 |  | 06 Feb 2023 |  | 0 | 0 | 163 | 0
3rd to 4th Slab (3rd Fl) - Col & Lift pardi (M35) | 64.86 | Cu.Mtr | 27 Aug 2022 |  | 06 Feb 2023 |  | 0 | 0 | 163 | 0
3RD FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
4th Slab (3rd Fl) - Slab, Beam & staircase (M30) | 212.73 | Cu.Mtr | 27 Aug 2022 |  | 18 Feb 2023 |  | 0 | 0 | 175 | 0
4th to 5th Slab (4th Fl) - Col & Lift pardi (M35) | 81.11 | Cu.Mtr | 27 Aug 2022 |  | 24 Feb 2023 |  | 0 | 0 | 181 | 0
4TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
5th Slab (4th Fl) - Slab, Beam & staircase (M30) | 212.88 | Cu.Mtr | 27 Aug 2022 |  | 10 Mar 2023 |  | 0 | 0 | 195 | 0
5th to 6th Slab (5th Fl) - Col & Lift pardi (M35) | 85.4 | Cu.Mtr | 27 Aug 2022 |  | 10 Mar 2023 |  | 0 | 0 | 195 | 0
5TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
6th Slab (5th Fl) - Slab, Beam & staircase (M30) | 212.88 | Cu.Mtr | 27 Aug 2022 |  | 12 Apr 2023 |  | 0 | 0 | 228 | 0
6th to 7th Slab (6th Fl) - Col & Lift pardi (M35) | 68.55 | Cu.Mtr | 27 Aug 2022 |  | 12 Apr 2023 |  | 0 | 0 | 228 | 0
6TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
7th Slab (6th Fl) - Slab, Beam & staircase (M30) | 204.8 | Cu.Mtr | 27 Aug 2022 |  | 25 Mar 2023 |  | 0 | 0 | 210 | 0
7th to 8th Slab (7th Fl) - Col & Lift pardi (M35) | 68.55 | Cu.Mtr | 27 Aug 2022 |  | 25 Mar 2023 |  | 0 | 0 | 210 | 0
7TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
8th Slab (7th Fl) - Slab, Beam & staircase (M30) | 212.88 | Cu.Mtr | 27 Aug 2022 |  | 01 Jun 2023 |  | 0 | 0 | 278 | 0
8th to 9th Slab (8th Fl) - Col & Lift pardi (M35) | 85.4 | Cu.Mtr | 27 Aug 2022 |  | 01 Jun 2023 |  | 0 | 0 | 278 | 0
8TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
9th Slab (8th Fl) - Slab, Beam & staircase (M30) | 212.88 | Cu.Mtr | 27 Aug 2022 |  | 10 May 2023 |  | 0 | 0 | 256 | 0
9th to 10th Slab (9th Fl) - Col & Lift pardi (M35) | 85.4 | Cu.Mtr | 27 Aug 2022 |  | 10 May 2023 |  | 0 | 0 | 256 | 0
9TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
10th Slab (9th Fl) - Slab, Beam & staircase (M30) | 212.88 | Cu.Mtr | 27 Aug 2022 |  | 12 Mar 2023 |  | 0 | 0 | 197 | 0
10th to 11th Slab (10th Fl) - Col & Lift pardi (M30) | 85.4 | Cu.Mtr | 27 Aug 2022 |  | 12 Mar 2023 |  | 0 | 0 | 197 | 0
10TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
11th Slab (10th Fl) - Slab, Beam & staircase (M30) | 212.88 | Cu.Mtr | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
11th to 12th Slab (11th Fl) - Col & Lift pardi (M30) | 85.4 | Cu.Mtr | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0 | Concrete Grade Change
11TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
12th Slab (11th Fl) - Slab, Beam & staircase (M30) | 212.88 | Cu.Mtr | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
12th to 13th Slab (12th Fl) - Col & Lift pardi (M30) | 85.4 | Cu.Mtr | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0 | Concrete Grade Change
12TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
13th Slab (12th Fl) - Slab, Beam & staircase (M30) | 212.88 | Cu.Mtr | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
13th to 14th Slab (13th Fl) - Col & Lift pardi (M30) | 85.4 | Cu.Mtr | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0 | Concrete Grade Change
13TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
14th Slab (13th Fl) - Slab, Beam & staircase (M30) | 212.88 | Cu.Mtr | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
14th to 15th Slab (14th Fl) - Col & Lift pardi (M30) | 85.4 | Cu.Mtr | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0 | Concrete Grade Change
14TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
15th Slab (14th Fl) - Slab, Beam & staircase (M30) | 212.88 | Cu.Mtr | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
15th to 16th Slab (15th Fl) - Col & Lift pardi (M30) | 85.4 | Cu.Mtr | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0 | Concrete Grade Change
15TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
16th Slab (15th Fl) - Slab, Beam & staircase (M30) | 212.88 | Cu.Mtr | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
16th to 17th Slab (16th Fl) - Col & Lift pardi (M30) | 85.4 | Cu.Mtr | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0 | Concrete Grade Change
16TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
17th Slab (16th Fl) - Slab, Beam & staircase (M30) | 212.88 | Cu.Mtr | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
17th to 18th Slab (17th Fl) - Col & Lift pardi (M30) | 85.4 | Cu.Mtr | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0 | Concrete Grade Change
TERRACE FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
18th Slab (Terrace Fl) - Slab, Beam & staircase (M30) | 212.88 | Cu.Mtr | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
18th to OHWT Slab (Terrace Fl) - Col & Lift pardi (M35) | 85.4 | Cu.Mtr | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
RCC WORK ORDER | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
RCC Work (Labour) | 0 | Sq.Ft | 27 Aug 2022 |  | 11 Nov 2022 |  | 0 | 0 | 76 | 0
COULPER WORK (L+M) | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Coupler Work - 1st to 2nd Slab | 1348 | Nos | 27 Aug 2022 |  | 17 Jan 2023 |  | 0 | 0 | 143 | 0
Coupler Work - 2nd to 3rd Slab | 1550 | Nos | 27 Aug 2022 |  | 17 Jan 2023 |  | 0 | 0 | 143 | 0
Coupler Work - 3rd to 4th Slab | 1314 | Nos | 27 Aug 2022 |  | 17 Jan 2023 |  | 0 | 0 | 143 | 0
Coupler Work - 4th to 5th Slab | 1204 | Nos | 27 Aug 2022 |  | 17 Jan 2023 |  | 0 | 0 | 143 | 0
Coupler Work - 5th to 6th Slab | 922 | Nos | 27 Aug 2022 |  | 20 Mar 2023 |  | 0 | 0 | 205 | 0
Coupler Work - 6th to 7th Slab | 650 | Nos | 27 Aug 2022 |  | 03 Apr 2023 |  | 0 | 0 | 219 | 0
Coupler Work - 7th to 8th Slab | 1040 | Nos | 27 Aug 2022 |  | 14 Apr 2023 |  | 0 | 0 | 230 | 0
Coupler Work - 8th to 9th Slab | 619 | Nos | 27 Aug 2022 |  | 03 May 2023 |  | 0 | 0 | 249 | 0
Coupler Work - 9th to 10th Slab | 462 | Nos | 27 Aug 2022 |  | 02 Jun 2023 |  | 0 | 0 | 279 | 0
Coupler Work - 10th to 11th Slab | 462 | Nos | 27 Aug 2022 |  | 27 Jul 2023 |  | 0 | 0 | 334 | 0
Coupler Work - 11th to 12th Slab | 210 | Nos | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Coupler Work - 12th to 13th Slab | 210 | Nos | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Coupler Work - 13th to 14th Slab | 210 | Nos | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Coupler Work - 14th to 15th Slab | 210 | Nos | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Coupler Work - 15th to 16th Slab | 210 | Nos | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Coupler Work - 16th to 17th Slab | 210 | Nos | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Coupler Work- 17th to 18th Slab | 210 | Nos | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Coupler Work- 18th to 19th Slab | 210 | Nos | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
MASONRY WORK | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
GROUND FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Ground Floor - Material For 5" AAC Block Brickwork | 14.35 | Cu.Mtrs | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Ground Floor - Material For 8" AAC Block Brickwork | 2.91 | Cu.Mtr | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Ground Floor - Material For DPC & Patli M20 | 1.76 | Cu.Mtr | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Ground Floor - Labour for Brickwork | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
1ST FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
1st Floor - Material For 5" AAC Block Brickwork | 98.03 | Cu.Mtrs | 27 Aug 2022 |  | 10 Mar 2023 |  | 0 | 0 | 195 | 0
1st Floor - Material For 8" AAC Block Brickwork | 7.94 | Cu.Mtr | 27 Aug 2022 |  | 10 Mar 2023 |  | 0 | 0 | 195 | 0
1st Floor - Material For 12" AAC Block Brickwork | 0.45 | Cu.Mtr | 27 Aug 2022 |  | 10 Mar 2023 |  | 0 | 0 | 195 | 0
1st Floor-Material For 5"FlyAsh Brickwork(Toilet & Dry Bal.) | 185.79 | Sq.Ft | 27 Aug 2022 |  | 10 Mar 2023 |  | 0 | 0 | 195 | 0
1st Floor - Material For DPC M20 | 22.02 | Cu.Mtr | 27 Aug 2022 |  | 10 Mar 2023 |  | 0 | 0 | 195 | 0
1st Floor - Material For 4" Red Brickwork | 263.69 | Sq.Ft | 27 Aug 2022 |  | 01 May 2023 |  | 0 | 0 | 247 | 0
1st Floor - Labour For Brickwork | 0 | Sq.Ft | 27 Aug 2022 |  | 10 Mar 2023 |  | 0 | 0 | 195 | 0
2ND FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
2nd Floor - Material For 5" AAC Block Brickwork | 98.03 | Cu.Mtrs | 27 Aug 2022 |  | 04 Apr 2023 |  | 0 | 0 | 220 | 0
2nd Floor - Material For 8" AAC Block Brickwork | 7.94 | Cu.Mtr | 27 Aug 2022 |  | 04 Apr 2023 |  | 0 | 0 | 220 | 0
2nd Floor - Material For 12" AAC Block Brickwork | 0.45 | Cu.Mtr | 27 Aug 2022 |  | 04 Apr 2023 |  | 0 | 0 | 220 | 0
2nd Floor-Material For 5"FlyAsh Brickwork(Toilet & Dry Bal.) | 185.79 | Sq.Ft | 27 Aug 2022 |  | 04 Apr 2023 |  | 0 | 0 | 220 | 0
2nd Floor - Material For DPC & Patli M20 | 22.02 | Cu.Mtr | 27 Aug 2022 |  | 04 Apr 2023 |  | 0 | 0 | 220 | 0
2nd Floor - Material For 4" Red Brickwork | 263.69 | Sq.Ft | 27 Aug 2022 |  | 15 May 2023 |  | 0 | 0 | 261 | 0
2nd Floor - Labour For Brickwork | 0 | Sq.Ft | 27 Aug 2022 |  | 04 Apr 2023 |  | 0 | 0 | 220 | 0
3RD FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
3rd Floor - Material For 5" AAC Block Brickwork | 97.57 | Cu.Mtrs | 27 Aug 2022 |  | 10 Apr 2023 |  | 0 | 0 | 226 | 0
3rd Floor - Material For 8" AAC Block Brickwork | 7.94 | Cu.Mtr | 27 Aug 2022 |  | 10 Apr 2023 |  | 0 | 0 | 226 | 0
3rd Floor - Material For 12" AAC Block Brickwork | 0.45 | Cu.Mtr | 27 Aug 2022 |  | 10 Apr 2023 |  | 0 | 0 | 226 | 0
3rd Floor-Material For 5"FlyAsh Brickwork(Toilet & Dry Bal.) | 185.79 | Sq.Ft | 27 Aug 2022 |  | 10 Apr 2023 |  | 0 | 0 | 226 | 0
3rd Floor - Material For DPC M20 | 22.02 | Cu.Mtr | 27 Aug 2022 |  | 10 Apr 2023 |  | 0 | 0 | 226 | 0
3rd Floor - Material For 4" Red Brickwork | 263.69 | Sq.Ft | 27 Aug 2022 |  | 10 Jul 2023 |  | 0 | 0 | 317 | 0
3rd Floor - Labour For Brickwork | 0 | Sq.Ft | 27 Aug 2022 |  | 10 Apr 2023 |  | 0 | 0 | 226 | 0
4TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
4th Floor - Material For 5" AAC Block Brickwork | 98.03 | Cu.Mtrs | 27 Aug 2022 |  | 10 May 2023 |  | 0 | 0 | 256 | 0 | quantity updated as per Pallavi Mam From 94.26 Cu.Mtr to 98.03 Cu.Mtr
4th Floor - Material For 8" AAC Block Brickwork | 7.94 | Cu.Mtr | 27 Aug 2022 |  | 10 May 2023 |  | 0 | 0 | 256 | 0
4th Floor - Material For 12" AAC Block Brickwork | 0.45 | Cu.Mtr | 27 Aug 2022 |  | 10 May 2023 |  | 0 | 0 | 256 | 0
4th Floor-Material For 5"FlyAsh Brickwork(Toilet & Dry Bal.) | 185.79 | Sq.Ft | 27 Aug 2022 |  | 10 May 2023 |  | 0 | 0 | 256 | 0
4th Floor - Material For DPC M20 | 7.2 | Cu.Mtr | 27 Aug 2022 |  | 13 May 2023 |  | 0 | 0 | 259 | 0 | DPC Thickness reduced & Patli cancelled as confirmed by Pallavi Mam Therefore quantity updated From 22.02 Cu.Mtr to 7.2 Cu.Mtr
4th Floor - Material For 4" Red Brickwork | 263.69 | Sq.Ft | 27 Aug 2022 |  | 10 May 2023 |  | 0 | 0 | 256 | 0
4th Floor - Labour For Brickwork | 0 | Sq.Ft | 27 Aug 2022 |  | 10 May 2023 |  | 0 | 0 | 256 | 0
5TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
5th Floor - Material For 5" AAC Block Brickwork | 97.26 | Cu.Mtrs | 27 Aug 2022 |  | 13 Jun 2023 |  | 0 | 0 | 290 | 0 | DPC Thickness decreased as checked by Pallavi Mam therefore quantity updated from 94.26 Cu.Mtrs to 97.26 Cu.Mtrs
5th Floor - Material For 8" AAC Block Brickwork | 7.94 | Cu.Mtr | 27 Aug 2022 |  | 13 Jun 2023 |  | 0 | 0 | 290 | 0
5th Floor-Material For 5"FlyAsh Brickwork(Toilet & Dry Bal.) | 185.79 | Sq.Ft | 27 Aug 2022 |  | 13 Jun 2023 |  | 0 | 0 | 290 | 0
5th Floor - Material For DPC M20 | 7.2 | Cu.Mtr | 27 Aug 2022 |  | 13 Jun 2023 |  | 0 | 0 | 290 | 0 | DPC Thickness reduced & Patli cancelled as confirmed by Pallavi Mam Therefore quantity updated From 22.02 Cu.Mtr to 7.2 Cu.Mtr
5th Floor - Material For 4" Red Brickwork | 263.69 | Sq.Ft | 27 Aug 2022 |  | 13 Jun 2023 |  | 0 | 0 | 290 | 0
5th Floor - Labour For Brickwork | 0 | Sq.Ft | 27 Aug 2022 |  | 13 Jun 2023 |  | 0 | 0 | 290 | 0
6TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
6th Floor - Material For 5" AAC Block Brickwork | 97.57 | Cu.Mtrs | 27 Aug 2022 |  | 10 Jul 2023 |  | 0 | 0 | 317 | 0 | DPC Thickness decreased as checked by Pallavi Mam therefore quantity updated from 94.26 Cu.Mtrs to 97.57 Cu.Mtrs
6th Floor - Material For 8" AAC Block Brickwork | 7.94 | Cu.Mtr | 27 Aug 2022 |  | 10 Jul 2023 |  | 0 | 0 | 317 | 0
6th Floor-Material For 5"FlyAsh Brickwork(Toilet & Dry Bal.) | 185.79 | Sq.Ft | 27 Aug 2022 |  | 10 Jul 2023 |  | 0 | 0 | 317 | 0
6th Floor - Material For DPC M20 | 7.2 | Cu.Mtr | 27 Aug 2022 |  | 10 Jul 2023 |  | 0 | 0 | 317 | 0 | DPC Thickness reduced & Patli cancelled as confirmed by Pallavi Mam Therefore quantity updated From 22.02 Cu.Mtr to 7.2 Cu.Mtr
6th Floor - Material For 4" Red Brickwork | 263.69 | Sq.Ft | 27 Aug 2022 |  | 10 Jul 2023 |  | 0 | 0 | 317 | 0
6th Floor - Labour For Brickwork | 0 | Sq.Ft | 27 Aug 2022 |  | 10 Jul 2023 |  | 0 | 0 | 317 | 0
7TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
7th Floor - Material For 5" AAC Block Brickwork | 97.57 | Cu.Mtrs | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0 | DPC Thickness decreased as checked by Pallavi Mam therefore quantity updated from 94.26 Cu.Mtrs to 97.57 Cu.Mtrs
7th Floor - Material For 8" AAC Block Brickwork | 7.94 | Cu.Mtr | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
7th Floor-Material For 5"FlyAsh Brickwork(Toilet & Dry Bal.) | 185.79 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
7th Floor - Material For DPC M20 | 7.2 | Cu.Mtr | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0 | DPC Thickness reduced & Patli cancelled as confirmed by Pallavi Mam Therefore quantity updated From 22.02 Cu.Mtr to 7.2 Cu.Mtr
7th Floor - Material For 4" Red Brickwork | 263.69 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
7th Floor - Labour For Brickwork | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
8TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
8th Floor - Material For 5" AAC Block Brickwork | 99.65 | Cu.Mtrs | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0 | DPC Thickness decreased as checked by Pallavi Mam therefore quantity updated from 94.26 Cu.Mtrs to 99.65 Cu.Mtrs 12'' AAC cancle & added to 5'' AAC
8th Floor - Material For 8" AAC Block Brickwork | 7.94 | Cu.Mtr | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
8th Floor-Material For 5"FlyAsh Brickwork(Toilet & Dry Bal.) | 187.078 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
8th Floor - Material For DPC M20 | 7.2 | Cu.Mtr | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0 | DPC Thickness reduced & Patli cancelled as confirmed by Pallavi Mam Therefore quantity updated From 22.02 Cu.Mtr to 7.2 Cu.Mtr
8th Floor - Material For 4" Red Brickwork | 263.69 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
8th Floor - Labour For Brickwork | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
9TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
9th Floor - Material For 5" AAC Block Brickwork | 97.57 | Cu.Mtrs | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0 | DPC Thickness decreased as checked by Pallavi Mam therefore quantity updated from 94.26 Cu.Mtrs to 97.57 Cu.Mtrs
9th Floor - Material For 8" AAC Block Brickwork | 7.94 | Cu.Mtr | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
9th Floor-Material For 5"FlyAsh Brickwork(Toilet & Dry Bal.) | 185.79 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
9th Floor - Material For DPC M20 | 7.2 | Cu.Mtr | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0 | DPC Thickness reduced & Patli cancelled as confirmed by Pallavi Mam Therefore quantity updated From 22.02 Cu.Mtr to 7.2 Cu.Mtr
9th Floor - Material For 4" Red Brickwork | 263.69 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
9th Floor - Labour For Brickwork | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
10TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
10th Floor - Material For 5" AAC Block Brickwork | 97.57 | Cu.Mtrs | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0 | DPC Thickness decreased as checked by Pallavi Mam therefore quantity updated from 94.26 Cu.Mtrs to 97.57 Cu.Mtrs
10th Floor - Material For 8" AAC Block Brickwork | 7.94 | Cu.Mtr | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
10th Floor-Material For 5"FlyAsh Brickwork(Toilet&Dry Bal.) | 185.79 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
10th Floor - Material For DPC M20 | 7.2 | Cu.Mtr | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0 | DPC Thickness reduced & Patli cancelled as confirmed by Pallavi Mam Therefore quantity updated From 22.02 Cu.Mtr to 7.2 Cu.Mtr
10th Floor - Material For 4" Red Brickwork | 263.69 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
10th Floor - Labour For Brickwork | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
11TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
11th Floor - Material For 5" AAC Block Brickwork | 97.57 | Cu.Mtrs | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0 | DPC Thickness decreased as checked by Pallavi Mam therefore quantity updated from 94.26 Cu.Mtrs to 97.57 Cu.Mtrs
11th Floor - Material For 8" AAC Block Brickwork | 7.94 | Cu.Mtr | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
11th Floor-Material For 5"FlyAsh Brickwork(Toilet&Dry Bal.) | 185.79 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
11th Floor - Material For DPC M20 | 7.2 | Cu.Mtr | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0 | DPC Thickness reduced & Patli cancelled as confirmed by Pallavi Mam Therefore quantity updated From 22.02 Cu.Mtr to 7.2 Cu.Mtr
11th Floor - Material For 4" Red Brickwork | 263.69 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
11th Floor - Labour For Brickwork | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
12TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
12th Floor - Material For 5" AAC Block Brickwork | 97.57 | Cu.Mtrs | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0 | DPC Thickness decreased as checked by Pallavi Mam therefore quantity updated from 94.26 Cu.Mtrs to 97.57 Cu.Mtrs
12th Floor - Material For 8" AAC Block Brickwork | 7.94 | Cu.Mtr | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
12th Floor-Material For 5"FlyAsh Brickwork(Toilet&Dry Bal.) | 185.79 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
12th Floor - Material For DPC M20 | 7.2 | Cu.Mtr | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0 | DPC Thickness reduced & Patli cancelled as confirmed by Pallavi Mam Therefore quantity updated From 22.02 Cu.Mtr to 7.2 Cu.Mtr
12th Floor - Material For 4" Red Brickwork | 263.69 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
12th Floor - Labour For Brickwork | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
13TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
13th Floor - Material For 5" AAC Block Brickwork | 97.57 | Cu.Mtrs | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0 | DPC Thickness decreased as checked by Pallavi Mam therefore quantity updated from 94.26 Cu.Mtrs to 97.57 Cu.Mtrs
13th Floor - Material For 8" AAC Block Brickwork | 7.94 | Cu.Mtr | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
13th Floor-Material For 5"FlyAsh Brickwork(Toilet&Dry Bal.) | 187.078 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
13th Floor - Material For DPC M20 | 7.2 | Cu.Mtr | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0 | DPC Thickness reduced & Patli cancelled as confirmed by Pallavi Mam Therefore quantity updated From 22.02 Cu.Mtr to 7.2 Cu.Mtr
13th Floor - Material For 4" Red Brickwork | 263.69 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
13th Floor - Labour For Brickwork | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
14TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
14th Floor - Material For 5" AAC Block Brickwork | 97.57 | Cu.Mtrs | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0 | DPC Thickness decreased as checked by Pallavi Mam therefore quantity updated from 94.26 Cu.Mtrs to 97.57 Cu.Mtrs
14th Floor - Material For 8" AAC Block Brickwork | 7.94 | Cu.Mtr | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
14th Floor-Material For 5"FlyAsh Brickwork(Toilet&Dry Bal.) | 185.79 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
14th Floor - Material For DPC M20 | 7.2 | Cu.Mtr | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0 | DPC Thickness reduced & Patli cancelled as confirmed by Pallavi Mam Therefore quantity updated From 22.02 Cu.Mtr to 7.2 Cu.Mtr
14th Floor - Material For 4" Red Brickwork | 263.69 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
14th Floor - Labour for Brickwork | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
15TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
15th Floor - Material For 5" AAC Block Brickwork | 97.57 | Cu.Mtrs | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0 | DPC Thickness decreased as checked by Pallavi Mam therefore quantity updated from 94.26 Cu.Mtrs to 97.57 Cu.Mtrs
15th Floor - Material For 8" AAC Block Brickwork | 7.94 | Cu.Mtr | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
15th Floor-Material For 5"FlyAsh Brickwork(Toilet&Dry Bal.) | 185.79 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
15th Floor - Material For DPC M20 | 7.2 | Cu.Mtr | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0 | DPC Thickness reduced confirmed by Pallavi Mam Therefore quantity updated From 22.02 Cu.Mtr to 7.2 Cu.Mtr
15th Floor - Material For 4" Red Brickwork | 263.69 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
15th Floor - Labour for Brickwork | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
16TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
16th Floor - Material For 5" AAC Block Brickwork | 97.57 | Cu.Mtrs | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0 | DPC Thickness decreased as checked by Pallavi Mam therefore quantity updated from 94.26 Cu.Mtrs to 97.57 Cu.Mtrs
16th Floor - Material For 8" AAC Block Brickwork | 7.94 | Cu.Mtr | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
16th Floor-Material For 5"FlyAsh Brickwork(Toilet&Dry Bal.) | 185.79 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
16th Floor - Material For DPC M20 | 7.2 | Cu.Mtr | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0 | DPC Thickness reduced & Patli cancelled as confirmed by Pallavi Mam Therefore quantity updated From 22.02 Cu.Mtr to 7.2 Cu.Mtr
16th Floor - Material For 4" Red Brickwork | 263.69 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
16th Floor - Labour for Brickwork | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
17TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
17th Floor - Labour for Brickwork | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
TERRACE FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Terrace Floor - Material For 5" AAC Block Brickwork | 97.57 | Cu.Mtrs | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0 | DPC Thickness decreased as checked by Pallavi Mam therefore quantity updated from 94.26 Cu.Mtrs to 97.57 Cu.Mtrs
Terrace Floor - Material For 8" AAC Block Brickwork | 7.94 | Cu.Mtr | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Terrace Floor - Material For 12" AAC Block Brickwork | 0.45 | Cu.Mtr | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Terrace Floor-Material For 5"FlyAsh Brickwork(Toilet&Dry Bal | 185.79 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Terrace Floor - Material For DPC M20 | 7.2 | Cu.Mtr | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0 | DPC Thickness reduced & Patli cancelled as confirmed by Pallavi Mam Therefore quantity updated From 22.02 Cu.Mtr to 7.2 Cu.Mtr
Terrace Floor - Material For 4" Red Brickwork | 263.69 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Terrace Floor - Labour for Brickwork | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
INTERNAL PLASTER WORK | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
GROUND FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Ground Floor - Material For Internal Plaster Work (Tar) | 1395.014 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Ground Floor - Labour For Internal Plaster Work (Tar) | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
1ST FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
1st Floor - Material For Internal Plaster Work (Tar & Sanla) | 23489.63 | Sq.Ft | 27 Aug 2022 |  | 20 Apr 2023 |  | 0 | 0 | 236 | 0
1st Floor - Labour For Internal Plaster Work (Tar & Sanla) | 0 | Sq.Ft | 27 Aug 2022 |  | 01 Apr 2023 |  | 0 | 0 | 217 | 0
2ND FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
2nd Floor - Material For Internal Plaster Work (Tar & Sanla) | 23489.63 | Sq.Ft | 27 Aug 2022 |  | 20 Apr 2023 |  | 0 | 0 | 236 | 0
2nd Floor - Labour For Internal Plaster Work (Tar & Sanla) | 0 | Sq.Ft | 27 Aug 2022 |  | 20 Apr 2023 |  | 0 | 0 | 236 | 0
3RD FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
3rd Floor - Material For Internal Plaster Work (Tar & Sanla) | 23489.63 | Sq.Ft | 27 Aug 2022 |  | 01 Jun 2023 |  | 0 | 0 | 278 | 0
3rd Floor - Labour For Internal Plaster Work (Tar & Plaster) | 0 | Sq.Ft | 27 Aug 2022 |  | 01 Jun 2023 |  | 0 | 0 | 278 | 0
4TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
4th Floor - Material For Internal Plaster Work (Tar & Sanla) | 23489.63 | Sq.Ft | 27 Aug 2022 |  | 01 Jun 2023 |  | 0 | 0 | 278 | 0
4th Floor - Labour For Internal Plaster Work (Tar & Sanla) | 0 | Sq.Ft | 27 Aug 2022 |  | 01 Jun 2023 |  | 0 | 0 | 278 | 0
5TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
5th Floor - Material For Internal Plaster (Tar & Sanla) | 23489.63 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
5th Floor - Labour For Internal Plaster Work (Tar & Sanla) | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
6TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
6th Floor - Material For Internal Plaster (Tar & Sanla) | 23489.63 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
6th Floor - Labour For Internal Plaster Work (Tar & Sanla) | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
7TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
7th Floor - Material For Internal Plaster Work (Tar & Sanla) | 23489.63 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
7th Floor - Labour For Internal Plaster Work (Tar & Sanla) | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
8TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
8th Floor - Material For Internal Plaster Work (Tar & Sanla) | 23038.3 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
8th Floor - Labour For Internal Plaster Work (Tar & Sanla) | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
9TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
9th Floor - Material For Internal Plaster Work (Tar & Sanla) | 23489.63 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
9th Floor - Labour For Internal Plaster Work (Tar & Sanla) | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
10TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
10th Floor -Material for Internal Plaster Work (Tar & Sanla) | 23489.63 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
10th Floor - Labour For Internal Plaster Work (Tar & Sanla) | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
11TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
11th Floor -Material For Internal Plaster Work (Tar & Sanla) | 23489.63 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
11th Floor - Labour For Internal Plaster Work (Tar & Sanla) | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
12TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
12th Floor -Material For Internal Plaster Work (Tar & Sanla) | 23489.63 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
12th Floor - Labour For Internal Plaster Work (Tar & Sanla) | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
13TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
13th Floor -Material For Internal Plaster Work (Tar & Sanla) | 23038.3 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
13th Floor - Labour For Internal Plaster Work (Tar & Sanla) | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
14TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
14th Floor -Material For Internal Plaster Work (Tar & Sanla) | 23489.63 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
14th Floor - Labour For Internal Plaster Work (Tar & Sanla) | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
15TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
15th Floor -Material For Internal Plaster Work (Tar & Sanla) | 23489.63 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
15th Floor - Labour For Internal Plaster Work (Tar & Sanla) | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
16TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
16th Floor -Material For Internal Plaster Work (Tar & Sanla) | 23489.63 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
16th Floor - Labour For Internal Plaster Work (Tar & Sanla) | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
17TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
17th Floor -Material For Internal Plaster Work (Tar & Sanla) | 23489.63 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
17th Floor - Labour For Internal Plaster Work (Tar & Sanla) | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
TERRACE FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Terrace Floor -Material For Internal Plaster Work (Tar & San | 23489.63 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Terrace Floor - Labour For Internal Plaster Work (Tar & Sanl | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
EXTERNAL PLASTER WORK | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
PARKING AREA, TOP TERRACE, STAIRCASE, LMR & OHWT PLASTER | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Parking Area - Material For External Plaster Work | 36964.01 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Top Terrace - Material For External Plaster Work | 10190.17 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Staircase - Material For External Plaster Work | 18255.31 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
LMR & OHWT - Material For External Plaster Work | 1069.73 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Labour For - Parking Area, Top Terrace, Staircase, LMR&OHWT | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
NORTH SIDE | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
North Side - Material For External Plaster Work | 37060.77 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
North Side - Labour For External Plaster Work | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
SOUTH SIDE | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
South Side - Material For External Plaster Work | 38997.86 | Sq.Ft | 27 Aug 2022 |  | 14 Apr 2023 |  | 0 | 0 | 230 | 0
South Side - Labour For External Plaster Work | 0 | Sq.Ft | 27 Aug 2022 |  | 14 Apr 2023 |  | 0 | 0 | 230 | 0
EAST SIDE | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
East Side - Material For External Plaster Work | 19755.49 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
East Side - Labour For External Plaster Work | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
WEST SIDE | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
West Side - Material For External Plaster Work | 19835.04 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
West Side - Labour For External Plaster Work | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
DUCT PLASTER | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Duct - Material For External Plaster Work | 73559.02 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Duct - Labour For External Plaster Work | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
WATERPROOFING WORK | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
1ST FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
1st Floor - Material For Waterproofing (Toilet & Dry Bal.) | 942.07 | Sq.Ft | 27 Aug 2022 |  | 01 May 2023 |  | 0 | 0 | 247 | 0
1st Floor-Material For Chemical Waterproofing (Att. Terrace) | 544.23 | Sq.Ft | 27 Aug 2022 |  | 01 May 2023 |  | 0 | 0 | 247 | 0
1st Floor - Labour For Conventional & Chemical Waterproofing | 1 | Job | 27 Aug 2022 |  | 01 May 2023 |  | 0 | 0 | 247 | 0
2ND FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
2nd Floor - Material For Waterproofing (Toilet & Dry Bal.) | 942.07 | Sq.Ft | 27 Aug 2022 |  | 01 May 2023 |  | 0 | 0 | 247 | 0
2nd Floor-Material For Chemical Waterproofing (Att. Terrace) | 544.23 | Sq.Ft | 27 Aug 2022 |  | 01 May 2023 |  | 0 | 0 | 247 | 0
2nd Floor - Labour For Conventional & Chemical Waterproofing | 1 | Job | 27 Aug 2022 |  | 01 May 2023 |  | 0 | 0 | 247 | 0
3RD FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
3rd Floor - Material For Waterproofing (Toilet & Dry Bal.) | 942.07 | Sq.Ft | 27 Aug 2022 |  | 01 Jun 2023 |  | 0 | 0 | 278 | 0
3rd Floor-Material For Chemical Waterproofing (Att. Terrace) | 544.23 | Sq.Ft | 27 Aug 2022 |  | 01 Jun 2023 |  | 0 | 0 | 278 | 0
3rd Floor - Labour For Conventional & Chemical Waterproofing | 1 | Job | 27 Aug 2022 |  | 01 Jun 2023 |  | 0 | 0 | 278 | 0
4TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
4th Floor - Material For Waterproofing (Toilet & Dry Bal.) | 942.07 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
4th Floor-Material For Chemical Waterproofing (Att. Terrace) | 544.23 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
4th Floor - Labour For Conventional & Chemical Waterproofing | 1 | Job | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
5TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
5th Floor - Material For Waterproofing (Toilet & Dry Bal.) | 942.07 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
5th Floor-Material For Chemical Waterproofing (Att. Terrace) | 544.23 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
5th Floor - Labour For Conventional & Chemical Waterproofing | 1 | Job | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
6TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
6th Floor - Material For Waterproofing (Toilet & Dry Bal.) | 942.07 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
6th Floor-Material For Chemical Waterproofing (Att. Terrace) | 544.23 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
6th Floor - Labour For Conventional & Chemical Waterproofing | 1 | Job | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
7TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
7th Floor - Material For Waterproofing (Toilet & Dry Bal.) | 942.07 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
7th Floor-Material For Chemical Waterproofing (Att. Terrace) | 544.23 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
7th Floor - Labour For Conventional & Chemical Waterproofing | 1 | Job | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
8TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
8th Floor - Material For Waterproofing (Toilet & Dry Bal.) | 942.07 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
8th Floor-Material For Chemical Waterproofing (Att. Terrace) | 520.65 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
8th Floor - Labour For Conventional & Chemical Waterproofing | 1 | Job | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
9TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
9th Floor - Material For Waterproofing (Toilet & Dry Bal.) | 942.07 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
9th Floor-Material For Chemical Waterproofing (Att. Terrace) | 544.23 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
9th Floor - Labour For Conventional & Chemical Waterproofing | 1 | Job | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
10TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
10th Floor - Material For Waterproofing (Toilet & Dry Bal.) | 942.07 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
10th Floor-Material For Chemical Waterproofing (Att. Terrace | 544.23 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
10th Floor - Labour For Conventional & Chemical Waterproofin | 1 | Job | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
11TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
11th Floor - Material For Waterproofing (Toilet & Dry Bal.) | 942.07 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
11th Floor-Material For Chemical Waterproofing (Att. Terrace | 544.23 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
11th Floor - Labour For Conventional & Chemical Waterproofin | 1 | Job | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
12TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
12th Floor - Material For Waterproofing (Toilet & Dry Bal.) | 942.07 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
12th Floor-Material For Chemical Waterproofing (Att. Terrace | 544.23 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
12th Floor - Labour For Conventional & Chemical Waterproofin | 1 | Job | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
13TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
13th Floor - Material For Waterproofing (Toilet & Dry Bal.) | 942.07 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
13th Floor-Material For Chemical Waterproofing (Att. Terrace | 520.65 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
13th Floor - Labour For Conventional & Chemical Waterproofin | 1 | Job | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
14TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
14th Floor - Material For Waterproofing (Toilet & Dry Bal.) | 942.07 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
14th Floor-Material For Chemical Waterproofing (Att. Terrace | 544.23 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
14th Floor - Labour For Conventional & Chemical Waterproofin | 1 | Job | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
15TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
15th Floor - Material For Waterproofing (Toilet & Dry Bal.) | 942.07 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
15th Floor-Material For Chemical Waterproofing (Att. Terrace | 544.23 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
15 Floor - Labour For Conventional & Chemical Waterproofing | 1 | Job | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
16TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
16th Floor - Material For Waterproofing (Toilet & Dry Bal.) | 942.07 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
16th Floor-Material For Chemical Waterproofing (Att. Terrace | 544.23 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
16th Floor - Labour For Conventional & Chemical Waterproofin | 1 | Job | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
17TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
17th Floor - Material For Waterproofing (Toilet & Dry Bal.) | 942.07 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
17th Floor-Material For Chemical Waterproofing (Att. Terrace | 544.23 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
17th Floor - Labour For Conventional & Chemical Waterproofin | 1 | Job | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
TERRACE FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Terrace Floor - Waterproofing At Top Terrace | 8496.78 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Terrace Floor - Labour For Conventional Waterproofing | 1 | Job | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
OHWT | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
OHWT - Material For Waterproofing Work | 1340.76 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
OHWT - Labour For Conventional Waterproofing | 1 | Job | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
TILING WORK | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
GROUND FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Ground Floor - Parking Flooring | 20583.89 | Sq.Ft | 27 Aug 2022 |  | 19 Jun 2023 |  | 0 | 0 | 296 | 0
Ground Floor - Entrance Lobby Flooring | 449.83 | Sq.Ft | 27 Aug 2022 |  | 19 Jun 2023 |  | 0 | 0 | 296 | 0
1ST FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
1st Floor - Flooring (Flat, Attach Terrace & Dry Balcony) | 7110.46 | Sq.Ft | 27 Aug 2022 |  | 27 Apr 2023 |  | 0 | 0 | 243 | 0
1st Floor - Flooring (Common & Master Toilets) | 661.56 | Sq.Ft | 27 Aug 2022 |  | 27 Apr 2023 |  | 0 | 0 | 243 | 0
1st Floor - Dado (Kitchen, Dry Balcony, Toilet & Washbasin) | 4679.54 | Sq.Ft | 27 Aug 2022 |  | 27 Apr 2023 |  | 0 | 0 | 243 | 0
1st Floor - Granite Work (For Flats Only) | 1154.79 | Sq.Ft | 27 Aug 2022 |  | 27 Apr 2023 |  | 0 | 0 | 243 | 0
1st Floor - Granite Work (Kitchen Platform) | 320.89 | Sq.Ft | 27 Aug 2022 |  | 27 Apr 2023 |  | 0 | 0 | 243 | 0
1st Floor - Flooring (Lift Lobbies) | 691.69 | Sq.Ft | 27 Aug 2022 |  | 01 Jun 2023 |  | 0 | 0 | 278 | 0
1st Floor - Granite Cladding Work (Lifts) | 94.83 | Sq.Ft | 27 Aug 2022 |  | 01 Jun 2023 |  | 0 | 0 | 278 | 0
2ND FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
2nd Floor - Flooring (Flat, Attach Terrace & Dry Balcony) | 7110.46 | Sq.Ft | 27 Aug 2022 |  | 01 Jun 2023 |  | 0 | 0 | 278 | 0
2nd Floor - Flooring (Common & Master Toilets) | 661.56 | Sq.Ft | 27 Aug 2022 |  | 01 Jun 2023 |  | 0 | 0 | 278 | 0
2nd Floor - Dado (Kitchen, Dry Balcony, Toilet & Washbasin) | 4679.54 | Sq.Ft | 27 Aug 2022 |  | 01 Jun 2023 |  | 0 | 0 | 278 | 0
2nd Floor - Granite Work (For Flats Only) | 1154.79 | Sq.Ft | 27 Aug 2022 |  | 01 Jun 2023 |  | 0 | 0 | 278 | 0
2nd Floor - Granite Work (Kitchen Platform) | 320.89 | Sq.Ft | 27 Aug 2022 |  | 01 Jun 2023 |  | 0 | 0 | 278 | 0
2nd Floor - Flooring (Lift Lobbies) | 691.69 | Sq.Ft | 27 Aug 2022 |  | 01 Jun 2023 |  | 0 | 0 | 278 | 0
2nd Floor - Granite Cladding Work (Lifts) | 94.83 | Sq.Ft | 27 Aug 2022 |  | 01 Jun 2023 |  | 0 | 0 | 278 | 0
3RD FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
3rd Floor - Flooring (Flat, Attach Terrace & Dry Balcony) | 7110.46 | Sq.Ft | 27 Aug 2022 |  | 01 Jun 2023 |  | 0 | 0 | 278 | 0
3rd Floor - Flooring (Common & Master Toilets) | 661.56 | Sq.Ft | 27 Aug 2022 |  | 01 Jun 2023 |  | 0 | 0 | 278 | 0
3rd Floor - Dado (Kitchen, Dry Balcony, Toilet & Washbasin) | 4679.54 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
3rd Floor - Granite Work (For Flats Only) | 1154.79 | Sq.Ft | 27 Aug 2022 |  | 01 Jun 2023 |  | 0 | 0 | 278 | 0
3rd Floor - Granite Work (Kitchen Platform) | 320.89 | Sq.Ft | 27 Aug 2022 |  | 01 Jun 2023 |  | 0 | 0 | 278 | 0
3rd Floor - Flooring (Lift Lobbies) | 691.69 | Sq.Ft | 27 Aug 2022 |  | 01 Jun 2023 |  | 0 | 0 | 278 | 0
3rd Floor - Granite Cladding Work (Lifts) | 94.83 | Sq.Ft | 27 Aug 2022 |  | 01 Jun 2023 |  | 0 | 0 | 278 | 0
4TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
4th Floor - Flooring (Flat, Attach Terrace & Dry Balcony) | 7110.46 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
4th Floor - Flooring (Common & Master Toilets) | 661.56 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
4th Floor - Dado (Kitchen, Dry Balcony, Toilet & Washbasin) | 4679.54 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
4th Floor - Granite Work (For Flats Only) | 1154.79 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
4th Floor - Granite Work (Kitchen Platform) | 320.89 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
4th Floor - Flooring (Lift Lobbies) | 691.69 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
4th Floor - Granite Cladding Work (Lifts) | 94.83 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
5TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
5th Floor - Flooring (Flat, Attach Terrace & Dry Balcony) | 7110.46 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
5th Floor - Flooring (Common & Master Toilets) | 661.56 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
5th Floor - Dado (Kitchen, Dry Balcony, Toilet & Washbasin) | 4679.54 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
5th Floor - Granite Work (For Flats Only) | 1154.79 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
5th Floor - Granite Work (Kitchen Platform) | 320.89 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
5th Floor - Flooring (Lift Lobbies) | 691.69 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
5th Floor - Granite Cladding Work (Lifts) | 94.83 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
6TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
6th Floor - Flooring (Flat, Attach Terrace & Dry Balcony) | 7110.46 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
6th Floor - Flooring (Common & Master Toilets) | 661.56 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
6th Floor - Dado (Kitchen, Dry Balcony, Toilet & Washbasin) | 4679.54 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
6th Floor - Granite Work (For Flats Only) | 1154.79 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
6th Floor - Granite Work (Kitchen Platform) | 320.89 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
6th Floor - Flooring (Lift Lobbies) | 691.69 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
6th Floor - Granite Cladding Work (Lifts) | 94.83 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
7TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
7th Floor - Flooring (Flat, Attach Terrace & Dry Balcony) | 7110.46 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
7th Floor - Flooring (Common & Master Toilets) | 661.56 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
7th Floor - Dado (Kitchen, Dry Balcony, Toilet & Washbasin) | 4679.54 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
7th Floor - Granite Work (For Flats Only) | 1154.79 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
7th Floor - Granite Work (Kitchen Platform) | 320.89 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
7th Floor - Flooring (Lift Lobbies) | 691.69 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
7th Floor - Granite Cladding Work (Lifts) | 94.83 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
8TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
8th Floor - Flooring (Flat, Attach Terrace & Dry Balcony) | 7110.46 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
8th Floor - Flooring (Common & Master Toilets) | 661.56 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
8th Floor - Dado (Kitchen, Dry Balcony, Toilet & Washbasin) | 4679.54 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
8th Floor - Granite Work (For Flats Only) | 1154.79 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
8th Floor - Granite Work (Kitchen Platform) | 320.89 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
8th Floor - Flooring (Lift Lobbies) | 691.69 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
8th Floor - Granite Cladding Work (Lifts) | 94.83 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
9TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
9th Floor - Flooring (Flat, Attach Terrace & Dry Balcony) | 7110.46 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
9th Floor - Flooring (Common & Master Toilets) | 661.56 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
9th Floor - Dado (Kitchen, Dry Balcony, Toilet & Washbasin) | 4679.54 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
9th Floor - Granite Work (For Flats Only) | 1154.79 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
9th Floor - Granite Work (Kitchen Platform) | 320.89 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
9th Floor - Flooring (Lift Lobbies) | 691.69 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
9th Floor - Granite Cladding Work (Lifts) | 94.83 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
10TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
10th Floor - Flooring (Flat, Attach Terrace & Dry Balcony) | 7110.46 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
10th Floor - Flooring (Common & Master Toilets) | 661.56 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
10th Floor - Dado (Kitchen, Dry Balcony, Toilet & Washbasin) | 4679.54 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
10th Floor - Granite Work (For Flats Only) | 1154.79 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
10th Floor - Granite Work (Kitchen Platform) | 320.89 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
10th Floor - Flooring (Lift Lobbies) | 691.69 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
10th Floor - Granite Cladding Work (Lifts) | 94.83 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
11TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
11th Floor - Flooring (Flat, Attach Terrace & Dry Balcony) | 7110.46 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
11th Floor - Flooring (Common & Master Toilets) | 661.56 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
11th Floor - Dado (Kitchen, Dry Balcony, Toilet & Washbasin) | 4679.54 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
11th Floor - Granite Work (For Flats Only) | 1154.79 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
11th Floor - Granite Work (Kitchen Platform) | 320.89 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
11th Floor - Flooring (Lift Lobbies) | 691.69 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
11th Floor - Granite Cladding Work (Lifts) | 94.83 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
12TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
12th Floor - Flooring (Flat, Attach Terrace & Dry Balcony) | 7110.46 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
12th Floor - Flooring (Common & Master Toilets) | 661.56 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
12th Floor - Dado (Kitchen, Dry Balcony, Toilet & Washbasin) | 4679.54 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
12th Floor - Granite Work (For Flats Only) | 1154.79 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
12th Floor - Granite Work (Kitchen Platform) | 320.89 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
12th Floor - Flooring (Lift Lobbies) | 691.69 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
12th Floor - Granite Cladding Work (Lifts) | 94.83 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
13TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
13th Floor - Flooring (Flat, Attach Terrace & Dry Balcony) | 7110.46 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
13th Floor - Flooring (Common & Master Toilets) | 661.56 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
13th Floor - Dado (Kitchen, Dry Balcony, Toilet & Washbasin) | 4679.54 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
13th Floor - Granite Work (For Flats Only) | 1154.79 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
13th Floor - Granite Work (Kitchen Platform) | 320.89 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
13th Floor - Flooring (Lift Lobbies) | 691.69 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
13th Floor - Granite Cladding Work (Lifts) | 94.83 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
14TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
14th Floor - Flooring (Flat, Attach Terrace & Dry Balcony) | 7110.46 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
14th Floor - Flooring (Common & Master Toilets) | 661.56 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
14th Floor - Dado (Kitchen, Dry Balcony, Toilet & Washbasin) | 4679.54 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
14th Floor - Granite Work (For Flats Only) | 1154.79 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
14th Floor - Granite Work (Kitchen Platform) | 320.89 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
14th Floor - Flooring (Lift Lobbies) | 691.69 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
14th Floor - Granite Cladding Work (Lifts) | 94.83 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
15TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
15th Floor - Flooring (Flat, Attach Terrace & Dry Balcony) | 7110.46 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
15th Floor - Flooring (Common & Master Toilets) | 661.56 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
15th Floor - Dado (Kitchen, Dry Balcony, Toilet & Washbasin) | 4679.54 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
15th Floor - Granite Work (For Flats Only) | 1154.79 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
15th Floor - Granite Work (Kitchen Platform) | 320.89 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
15th Floor - Flooring (Lift Lobbies) | 691.69 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
15th Floor - Granite Cladding Work (Lifts) | 94.83 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
16TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
16th Floor - Flooring (Flat, Attach Terrace & Dry Balcony) | 7110.46 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
16th Floor - Flooring (Common & Master Toilets) | 661.56 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
16th Floor - Dado (Kitchen, Dry Balcony, Toilet & Washbasin) | 4679.54 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
16th Floor - Granite Work (For Flats Only) | 1154.79 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
16th Floor - Granite Work (Kitchen Platform) | 320.89 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
16th Floor - Flooring (Lift Lobbies) | 691.69 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
16th Floor - Granite Cladding Work (Lifts) | 94.83 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
17TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
17th Floor - Flooring (Flat, Attach Terrace & Dry Balcony) | 7110.46 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
17th Floor - Flooring (Common & Master Toilets) | 661.56 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
17th Floor - Dado (Kitchen, Dry Balcony, Toilet & Washbasin) | 4679.54 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
17th Floor - Granite Work (For Flats Only) | 1154.79 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
17th Floor - Granite Work (Kitchen Platform) | 320.89 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
17th Floor - Flooring (Lift Lobbies) | 691.69 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
17th Floor - Granite Cladding Work (Lifts) | 94.83 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
STAIRCASE | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Staircase - Flooring (Tread & Riser (Tappa)) | 2584.4 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Staircase - Landing & Midlanding Flooring | 2023.81 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
FIRE STAIRCASE | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Fire Staircase - Flooring (Tread & Riser (Tappa)) | 1812.31 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Fire Staircase - Landing & Midlanding Flooring | 1309.4 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
GYPSUM PUNNING WORK (L+M) | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
GROUND FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
1ST FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
1st Floor- Flats Gypsum Punning Work | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
1st Floor- Lift Lobbies Gypsum Punning Work | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
1st Floor - Gypsum Punning Work (Material) | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
2ND FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
2nd Floor- Flats Gypsum Punning Work | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
2nd Floor- Lift Lobbies Gypsum Punning Work | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
2nd Floor - Gypsum Punning Work (Material) | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
3RD FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
3rd Floor- Flats Gypsum Punning Work | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
3rd Floor- Lift Lobbies Gypsum Punning Work | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
3rd Floor - Gypsum Punning Work (Material) | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
4TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
4th Floor- Flats Gypsum Punning Work | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
4th Floor- Lift Lobbies Gypsum Punning Work | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
4th Floor - Gypsum Punning Work (Material) | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
5TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
5th Floor- Flats Gypsum Punning Work | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
5th Floor- Lift Lobbies Gypsum Punning Work | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
5th Floor - Gypsum Punning Work (Material) | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
6TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
6th Floor- Flats Gypsum Punning Work | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
6th Floor- Lift Lobbies Gypsum Punning Work | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
6th Floor - Gypsum Punning Work (Material) | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
7TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
7th Floor- Flats Gypsum Punning Work | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
7th Floor- Lift Lobbies Gypsum Punning Work | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
7th Floor - Gypsum Punning Work (Material) | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
8TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
8th Floor- Flats Gypsum Punning Work | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
8th Floor- Lift Lobbies Gypsum Punning Work | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
8th Floor - Gypsum Punning Work (Material) | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
9TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
9th Floor- Flats Gypsum Punning Work | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
9th Floor- Lift Lobbies Gypsum Punning Work | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
9th Floor - Gypsum Punning Work (Material) | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
10TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
10th Floor- Flats Gypsum Punning Work | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
10th Floor- Lift Lobbies Gypsum Punning Work | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
10th Floor - Gypsum Punning Work (Material) | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
11TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
11th Floor- Flats Gypsum Punning Work | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
1st Floor- Lift Lobbies Gypsum Punning Work | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
11th Floor - Gypsum Punning Work (Material) | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
12TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
12th Floor- Flats Gypsum Punning Work | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
12th Floor- Lift Lobbies Gypsum Punning Work | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
12th Floor - Gypsum Punning Work (Material) | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
13TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
13th Floor- Flats Gypsum Punning Work | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
13th Floor- Lift Lobbies Gypsum Punning Work | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
13th Floor - Gypsum Punning Work (Material) | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
14TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
14th Floor- Flats Gypsum Punning Work | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
14th Floor- Lift Lobbies Gypsum Punning Work | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
14th Floor - Gypsum Punning Work (Material) | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
15TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
15th Floor- Flats Gypsum Punning Work | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
15th Floor- Lift Lobbies Gypsum Punning Work | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
15th Floor - Gypsum Punning Work (Material) | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
16TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
16th Floor- Flats Gypsum Punning Work | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
16th Floor- Lift Lobbies Gypsum Punning Work | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
16th Floor - Gypsum Punning Work (Material) | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
17TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
17th Floor- Flats Gypsum Punning Work | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
17th Floor- Lift Lobbies Gypsum Punning Work | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
17th Floor - Gypsum Punning Work (Material) | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
FIRE STAIRCASE | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Fire Staircase- Gypsum Punning Work | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
STAIRCASE | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Staircase- Gypsum Punning Work | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
INTERNAL PAINTING WORK (L+M) | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
GROUND FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Ground Floor - Internal Painting Work (L+M) | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
1ST FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
1st Floor - Internal Painting Work (L+M) | 0 | Sq.Ft | 27 Aug 2022 |  | 25 Mar 2023 |  | 0 | 0 | 210 | 0
2ND FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
2nd Floor - Internal Painting Work (L+M) | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
3RD FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
3rd Floor - Internal Painting Work (L+M) | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
4TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
4th Floor - Internal Painting Work (L+M) | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
5TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
5th Floor - Internal Painting Work (L+M) | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
6TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
6th Floor - Internal Painting Work (L+M) | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
7TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
7th Floor - Internal Painting Work (L+M) | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
8TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
8th Floor - Internal Painting Work (L+M) | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
9TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
9th Floor - Internal Painting Work (L+M) | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
10TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
10th Floor - Internal Painting Work (L+M) | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
11TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
1th Floor - Internal Painting Work (L+M) | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
12TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
12th Floor - Internal Painting Work (L+M) | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
13TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
13th Floor - Internal Painting Work (L+M) | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
14TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
14th Floor - Internal Painting Work (L+M) | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
15TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
15th Floor - Internal Painting Work (L+M) | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
16TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
16th Floor - Internal Painting Work (L+M) | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
17TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
17th Floor - Internal Painting Work (L+M) | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
FIRE STAIRCASE | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Fire Staircase - Internal Painting Work (L+M) | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Fire Staircase - Oil Painting Work (L+M) | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
STAIRCASE | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Staircase - Internal Painting Work (L+M) | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Staircase - Oil Painting Work (L+M) | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
LIFT | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Lift Shaft - Internal Painting Work (L+M) | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
EXTERNAL PAINTING WORK (L+M) | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
FIRE STAIRCASE | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Fire Staircase - External Painting Work (L+M) | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
STAIRCASE | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Staircase - External Painting Work (L+M) | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
TERRACE FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Terrace Floor - External Painting Work (L+M) | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
ALL SIDES - EXTERNAL WALLS & CEILING | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
External Painting Work-Attached Terrace Ceiling & Walls(L+M) | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
External Painting Work- Dry Balcony Walls (L+M) | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
External Painting Work- All Sides External Walls (L+M) | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
DUCTS | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Ducts - External Painting Work (L+M) | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
ELECTRICAL WORK | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
1ST FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
1st Floor - Wall Conduiting Work (Material) | 0 | No. | 27 Aug 2022 |  | 01 May 2023 |  | 0 | 0 | 247 | 0
1st Floor - Electrical DB Fitting Work (Material) | 0 | No. | 27 Aug 2022 |  | 01 May 2023 |  | 0 | 0 | 247 | 0
1st Floor - Wiring Work (Material) | 0 | No. | 27 Aug 2022 |  | 01 May 2023 |  | 0 | 0 | 247 | 0
1st Floor - Electrical Fittings & Accessories (Material) | 0 | No. | 27 Aug 2022 |  | 01 May 2023 |  | 0 | 0 | 247 | 0
1st Floor - Labour For Electrical Work | 0 | No. | 27 Aug 2022 |  | 01 May 2023 |  | 0 | 0 | 247 | 0
2ND FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
2nd Floor- 3rd Slab Conduiting Work (Material) | 0 | Per Floor | 27 Aug 2022 |  | 31 Jan 2023 |  | 0 | 0 | 157 | 0
2nd Floor - Wall Conduiting Work (Material) | 0 | No. | 27 Aug 2022 |  | 01 May 2023 |  | 0 | 0 | 247 | 0
2nd Floor - Electrical DB Fitting Work (Material) | 0 | No. | 27 Aug 2022 |  | 01 May 2023 |  | 0 | 0 | 247 | 0
2nd Floor - Wiring Work (Material) | 0 | No. | 27 Aug 2022 |  | 01 May 2023 |  | 0 | 0 | 247 | 0
2nd Floor - Electrical Fittings & Accessories (Material) | 0 | No. | 27 Aug 2022 |  | 01 May 2023 |  | 0 | 0 | 247 | 0
2nd Floor - Labour For Electrical Work | 0 | No. | 27 Aug 2022 |  | 01 May 2023 |  | 0 | 0 | 247 | 0
3RD FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
3rd Floor- 4th Slab Conduiting Work (Material) | 0 | Per Floor | 27 Aug 2022 |  | 20 Feb 2023 |  | 0 | 0 | 177 | 0
3rd Floor - Wall Conduiting Work (Material) | 0 | No. | 27 Aug 2022 |  | 01 May 2023 |  | 0 | 0 | 247 | 0
3rd Floor - Electrical DB Fitting Work (Material) | 0 | No. | 27 Aug 2022 |  | 01 May 2023 |  | 0 | 0 | 247 | 0
3rd Floor - Wiring Work (Material) | 0 | No. | 27 Aug 2022 |  | 01 May 2023 |  | 0 | 0 | 247 | 0
3rd Floor - Electrical Fittings & Accessories (Material) | 0 | No. | 27 Aug 2022 |  | 01 May 2023 |  | 0 | 0 | 247 | 0
3rd Floor - Labour For Electrical Work | 0 | No. | 27 Aug 2022 |  | 01 May 2023 |  | 0 | 0 | 247 | 0
4TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
4th Floor- 5th Slab Conduiting Work (Material) | 0 | Per Floor | 27 Aug 2022 |  | 11 Mar 2023 |  | 0 | 0 | 196 | 0
4th Floor - Wall Conduiting Work (Material) | 0 | No. | 27 Aug 2022 |  | 01 Apr 2023 |  | 0 | 0 | 217 | 0
4th Floor - Electrical DB Fitting Work (Material) | 0 | No. | 27 Aug 2022 |  | 01 Apr 2023 |  | 0 | 0 | 217 | 0
4th Floor - Wiring Work (Material) | 0 | No. | 27 Aug 2022 |  | 01 Apr 2023 |  | 0 | 0 | 217 | 0
4th Floor - Electrical Fittings & Accessories (Material) | 0 | No. | 27 Aug 2022 |  | 01 Apr 2023 |  | 0 | 0 | 217 | 0
4th Floor - Labour For Electrical Work | 0 | No. | 27 Aug 2022 |  | 01 Apr 2023 |  | 0 | 0 | 217 | 0
5TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
5th Floor- 6th Slab Conduiting Work (Material) | 0 | Per Floor | 27 Aug 2022 |  | 31 Mar 2023 |  | 0 | 0 | 216 | 0
5th Floor - Wall Conduiting Work (Material) | 0 | No. | 27 Aug 2022 |  | 01 Apr 2023 |  | 0 | 0 | 217 | 0
5th Floor - Electrical DB Fitting Work (Material) | 0 | No. | 27 Aug 2022 |  | 01 Apr 2023 |  | 0 | 0 | 217 | 0
5th Floor - Wiring Work (Material) | 0 | No. | 27 Aug 2022 |  | 01 Apr 2023 |  | 0 | 0 | 217 | 0
5th Floor - Electrical Fittings & Accessories (Material) | 0 | No. | 27 Aug 2022 |  | 01 Apr 2023 |  | 0 | 0 | 217 | 0
5th Floor - Labour For Electrical Work | 0 | No. | 27 Aug 2022 |  | 01 Apr 2023 |  | 0 | 0 | 217 | 0
6TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
6th Floor- 7th Slab Conduiting Work (Material) | 0 | Per Floor | 27 Aug 2022 |  | 01 Apr 2023 |  | 0 | 0 | 217 | 0
6th Floor - Wall Conduiting Work (Material) | 0 | No. | 27 Aug 2022 |  | 01 Apr 2023 |  | 0 | 0 | 217 | 0
6th Floor - Electrical DB Fitting Work (Material) | 0 | No. | 27 Aug 2022 |  | 01 Apr 2023 |  | 0 | 0 | 217 | 0
6th Floor - Wiring Work (Material) | 0 | No. | 27 Aug 2022 |  | 01 Apr 2023 |  | 0 | 0 | 217 | 0
6th Floor - Electrical Fittings & Accessories (Material) | 0 | No. | 27 Aug 2022 |  | 01 Apr 2023 |  | 0 | 0 | 217 | 0
6th Floor - Labour For Electrical Work | 0 | No. | 27 Aug 2022 |  | 01 Apr 2023 |  | 0 | 0 | 217 | 0
7TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
7th Floor- 8th Slab Conduiting Work (Material) | 0 | Per Floor | 27 Aug 2022 |  | 01 May 2023 |  | 0 | 0 | 247 | 0
7th Floor - Wall Conduiting Work (Material) | 0 | No. | 27 Aug 2022 |  | 01 May 2023 |  | 0 | 0 | 247 | 0
7th Floor - Electrical DB Fitting Work (Material) | 0 | No. | 27 Aug 2022 |  | 01 May 2023 |  | 0 | 0 | 247 | 0
7th Floor - Wiring Work (Material) | 0 | No. | 27 Aug 2022 |  | 01 May 2023 |  | 0 | 0 | 247 | 0
7th Floor - Electrical Fittings & Accessories (Material) | 0 | No. | 27 Aug 2022 |  | 01 May 2023 |  | 0 | 0 | 247 | 0
7th Floor - Labour For Electrical Work | 0 | No. | 27 Aug 2022 |  | 01 May 2023 |  | 0 | 0 | 247 | 0
8TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
8th Floor- 9th Slab Conduiting Work (Material) | 0 | Per Floor | 27 Aug 2022 |  | 01 May 2023 |  | 0 | 0 | 247 | 0
8th Floor - Wall Conduiting Work (Material) | 0 | No. | 27 Aug 2022 |  | 15 Jun 2023 |  | 0 | 0 | 292 | 0
8th Floor - Electrical DB Fitting Work (Material) | 0 | No. | 27 Aug 2022 |  | 01 May 2023 |  | 0 | 0 | 247 | 0
8th Floor - Wiring Work (Material) | 0 | No. | 27 Aug 2022 |  | 01 May 2023 |  | 0 | 0 | 247 | 0
8th Floor - Electrical Fittings & Accessories (Material) | 0 | No. | 27 Aug 2022 |  | 01 May 2023 |  | 0 | 0 | 247 | 0
8th Floor - Labour For Electrical Work | 0 | No. | 27 Aug 2022 |  | 01 May 2023 |  | 0 | 0 | 247 | 0
9TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
9th Floor- 10th Slab Conduiting Work (Material) | 0 | Per Floor | 27 Aug 2022 |  | 15 Jun 2023 |  | 0 | 0 | 292 | 0
9th Floor - Wall Conduiting Work (Material) | 0 | No. | 27 Aug 2022 |  | 15 Jun 2023 |  | 0 | 0 | 292 | 0
9th Floor - Electrical DB Fitting Work (Material) | 0 | No. | 27 Aug 2022 |  | 15 Jun 2023 |  | 0 | 0 | 292 | 0
9th Floor - Wiring Work (Material) | 0 | No. | 27 Aug 2022 |  | 15 Jun 2023 |  | 0 | 0 | 292 | 0
9th Floor - Electrical Fittings & Accessories (Material) | 0 | No. | 27 Aug 2022 |  | 15 Jun 2023 |  | 0 | 0 | 292 | 0
9th Floor - Labour For Electrical Work | 0 | No. | 27 Aug 2022 |  | 15 Jun 2023 |  | 0 | 0 | 292 | 0
10TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
10th Floor- 11th Slab Conduiting Work (Material) | 0 | Per Floor | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
10th Floor - Wall Conduiting Work (Material) | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
10th Floor - Electrical DB Fitting Work (Material) | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
10th Floor - Wiring Work (Material) | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
10th Floor - Electrical Fittings & Accessories (Material) | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
10th Floor - Labour For Electrical Work | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
11TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
11th Floor- 12th Slab Conduiting Work (Material) | 0 | Per Floor | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
11th Floor - Wall Conduiting Work (Material) | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
11th Floor - Electrical DB Fitting Work (Material) | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
11th Floor - Wiring Work (Material) | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
11th Floor - Electrical Fittings & Accessories (Material) | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
11th Floor - Labour For Electrical Work | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
12TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
12th Floor- 13th Slab Conduiting Work (Material) | 0 | Per Floor | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
12th Floor - Wall Conduiting Work (Material) | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
12th Floor - Electrical DB Fitting Work (Material) | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
12th Floor - Wiring Work (Material) | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
12th Floor - Electrical Fittings & Accessories (Material) | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
12th Floor - Labour For Electrical Work | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
13TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
13th Floor- 14th Slab Conduiting Work (Material) | 0 | Per Floor | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
13th Floor - Wall Conduiting Work (Material) | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
13th Floor - Electrical DB Fitting Work (Material) | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
13th Floor - Wiring Work (Material) | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
13th Floor - Electrical Fittings & Accessories (Material) | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
13th Floor - Labour For Electrical Work | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
14TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
14th Floor- 15th Slab Conduiting Work (Material) | 0 | Per Floor | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
14th Floor - Wall Conduiting Work (Material) | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
14th Floor - Electrical DB Fitting Work (Material) | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
14th Floor - Wiring Work (Material) | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
14th Floor - Electrical Fittings & Accessories (Material) | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
14th Floor - Labour For Electrical Work | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
15TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
15th Floor- 16th Slab Conduiting Work (Material) | 0 | Per Floor | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
15th Floor - Wall Conduiting Work (Material) | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
15th Floor - Electrical DB Fitting Work (Material) | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
15th Floor - Wiring Work (Material) | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
15th Floor - Electrical Fittings & Accessories (Material) | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
15th Floor - Labour For Electrical Work | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
16TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
16th Floor- 17th Slab Conduiting Work (Material) | 0 | Per Floor | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
16th Floor - Wall Conduiting Work (Material) | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
16th Floor - Electrical DB Fitting Work (Material) | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
16th Floor - Wiring Work (Material) | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
16th Floor - Electrical Fittings & Accessories (Material) | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
16th Floor - Labour For Electrical Work | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
17TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
17th Floor- 18th Slab Conduiting Work (Material) | 0 | Per Floor | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
17th Floor - Wall Conduiting Work (Material) | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
17th Floor - Electrical DB Fitting Work (Material) | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
17th Floor - Wiring Work (Material) | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
17th Floor - Electrical Fittings & Accessories (Material) | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
17th Floor - Labour For Electrical Work | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
INTERNAL PLUMBING WORK | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
1ST FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
1st Floor- Internal Plumbing Concealed CPVC Lines (Material) | 0 | No. | 27 Aug 2022 |  | 27 Apr 2023 |  | 0 | 0 | 243 | 0
1st Floor- Huliot (Material) | 0 | No. | 27 Aug 2022 |  | 27 Apr 2023 |  | 0 | 0 | 243 | 0
1st Floor- CP & Sanitary Fittings (Material) | 0 | No. | 27 Aug 2022 |  | 01 Jul 2023 |  | 0 | 0 | 308 | 0
1st Floor - Labour For Plumbing Work | 0 | Job | 27 Aug 2022 |  | 01 May 2023 |  | 0 | 0 | 247 | 0
2ND FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
2nd Floor- Internal Plumbing Concealed CPVC Lines (Material) | 0 | No. | 27 Aug 2022 |  | 01 Jun 2023 |  | 0 | 0 | 278 | 0
2nd Floor- Huliot (Material) | 0 | No. | 27 Aug 2022 |  | 01 Jun 2023 |  | 0 | 0 | 278 | 0
2nd Floor- CP & Sanitary Fittings (Material) | 0 | No. | 27 Aug 2022 |  | 01 Jun 2023 |  | 0 | 0 | 278 | 0
2nd Floor - Labour For Plumbing Work | 0 | Job | 27 Aug 2022 |  | 01 Jun 2023 |  | 0 | 0 | 278 | 0
3RD FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
3rd Floor- Internal Plumbing Concealed CPVC Lines (Material) | 0 | No. | 27 Aug 2022 |  | 01 Jun 2023 |  | 0 | 0 | 278 | 0
3rd Floor- Huliot (Material) | 0 | No. | 27 Aug 2022 |  | 01 Jun 2023 |  | 0 | 0 | 278 | 0
3rd Floor- CP & Sanitary Fittings (Material) | 0 | No. | 27 Aug 2022 |  | 01 Jun 2023 |  | 0 | 0 | 278 | 0
2nd Floor- Internal Plumbing Concealed CPVC Lines (Material) | 0 | No. | 27 Aug 2022 |  | 01 Jun 2023 |  | 0 | 0 | 278 | 0
3rd Floor - Labour For Plumbing Work | 0 | Job | 27 Aug 2022 |  | 01 Jun 2023 |  | 0 | 0 | 278 | 0
4TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
4th Floor- Internal Plumbing Concealed CPVC Lines (Material) | 0 | No. | 27 Aug 2022 |  | 01 Jun 2023 |  | 0 | 0 | 278 | 0
4th Floor- Huliot (Material) | 0 | No. | 27 Aug 2022 |  | 01 Jun 2023 |  | 0 | 0 | 278 | 0
4th Floor- CP & Sanitary Fittings (Material) | 0 | No. | 27 Aug 2022 |  | 01 Jun 2023 |  | 0 | 0 | 278 | 0
4th Floor - Labour For Plumbing Work | 0 | Job | 27 Aug 2022 |  | 01 Jun 2023 |  | 0 | 0 | 278 | 0
5TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
5th Floor- Internal Plumbing Concealed CPVC Lines (Material) | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
5th Floor- Huliot (Material) | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
5th Floor- CP & Sanitary Fittings (Material) | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
5th Floor - Labour For Plumbing Work | 0 | Job | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
6TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
6th Floor- Internal Plumbing Concealed CPVC Lines (Material) | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
6th Floor- Huliot (Material) | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
6th Floor- CP & Sanitary Fittings (Material) | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
6th Floor - Labour For Plumbing Work | 0 | Job | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
7TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
7th Floor- Internal Plumbing Concealed CPVC Lines (Material) | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
7th Floor- Huliot (Material) | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
7th Floor- CP & Sanitary Fittings (Material) | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
7th Floor - Labour For Plumbing Work | 0 | Job | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
8TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
8th Floor- Internal Plumbing Concealed CPVC Lines (Material) | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
8th Floor. Huliot (Material) | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
8th Floor- CP & Sanitary Fittings (Material) | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
8th Floor - Labour For Plumbing Work | 0 | Job | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
9TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
9th Floor- Internal Plumbing Concealed CPVC Lines (Material) | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
9th Floor. Huliot (Material) | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
9th Floor- CP & Sanitary Fittings (Material) | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
9th Floor - Labour For Plumbing Work | 0 | Job | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
10TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
10th Floor- Internal Plumbing Concealed CPVC Lines(Material) | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
10th Floor. Huliot (Material) | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
10th Floor- CP & Sanitary Fittings (Material) | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
10th Floor - Labour For Plumbing Work | 0 | Job | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
11TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
11th Floor -Internal Plumbing Concealed CPVC Lines(Material) | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
11th Floor. Huliot (Material) | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
11th Floor- CP & Sanitary Fittings (Material) | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
11th Floor - Labour For Plumbing Work | 0 | Job | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
12TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
12th Floor -Internal Plumbing Concealed CPVC Lines(Material) | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
12th Floor. Huliot (Material) | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
12th Floor- CP & Sanitary Fittings (Material) | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
12th Floor - Labour For Plumbing Work | 0 | Job | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
13TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
13th Floor- Internal Plumbing Concealed CPVC Lines (Material | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
13th Floor. Huliot (Material) | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
13th Floor- CP & Sanitary Fittings (Material) | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
13th Floor - Labour For Plumbing Work | 0 | Job | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
14TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
14th Floor- Internal Plumbing Concealed CPVC Lines (Material | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
14th Floor. Huliot (Material) | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
14th Floor- CP & Sanitary Fittings (Material) | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
14th Floor - Labour For Plumbing Work | 0 | Job | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
15TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
15th Floor- Internal Plumbing Concealed CPVC Lines (Material | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
15th Floor. Huliot (Material) | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
15th Floor- CP & Sanitary Fittings (Material) | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
15 Floor - Labour For Plumbing Work | 0 | Job | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
16TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
16th Floor- Internal Plumbing Concealed CPVC Lines (Material | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
16th Floor. Huliot (Material) | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
16th Floor- CP & Sanitary Fittings (Material) | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
16th Floor - Labour For Plumbing Work | 0 | Job | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
17TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
17th Floor- Internal Plumbing Concealed CPVC Lines (Material | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
17th Floor. Huliot (Material) | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
17th Floor- CP & Sanitary Fittings (Material) | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
17th Floor - Labour For Plumbing Work | 0 | Job | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
EXTERNAL PLUMBING WORK | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
EXTERNAL PLUMBING | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
External Plumbing UPVC & PVC Downtake Lines (Cold/Hot water, | 0 | No. | 27 Aug 2022 |  | 20 Apr 2023 |  | 0 | 0 | 236 | 0
DOOR WORK (L+M) | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
WOODEN DOOR WORK | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
1ST FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
1st Floor- Material Door Hardware | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
1st Floor- Door Frames & Shutters (L+M) | 57 | Nos | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
1st Floor- Door Frames & Shutters (L) | 57 | Nos | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
2ND FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
2nd Floor- Material Door Hardware | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
2nd Floor- Door Frames & Shutters (L+M) | 57 | Nos | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
2nd Floor- Door Frames & Shutters (L) | 57 | Nos | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
3RD FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
3rd Floor- Material Door Hardware | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
3rd Floor- Door Frames & Shutters (L+M) | 57 | Nos | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
3rd Floor- Door Frames & Shutters (L) | 57 | Nos | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
4TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
4th Floor- Material Door Hardware | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
4th Floor- Door Frames & Shutters (L+M) | 57 | Nos | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
4th Floor- Door Frames & Shutters (L) | 57 | Nos | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
5TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
5th Floor- Material Door Hardware | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
5th Floor- Door Frames & Shutters (L+M) | 57 | Nos | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
5th Floor- Door Frames & Shutters (L) | 57 | Nos | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
6TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
6th Floor- Material Door Hardware | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
6th Floor- Door Frames & Shutters (L+M) | 57 | Nos | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
6th Floor- Door Frames & Shutters (L) | 57 | Nos | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
7TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
7th Floor- Material Door Hardware | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
7th Floor- Door Frames & Shutters (L+M) | 57 | Nos | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
7th Floor- Door Frames & Shutters (L) | 57 | Nos | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
8TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
8th Floor- Material Door Hardware | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
8th Floor- Door Frames & Shutters (L+M) | 57 | Nos | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
8th Floor- Door Frames & Shutters (L) | 57 | Nos | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
9TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
9th Floor- Material Door Hardware | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
9th Floor- Door Frames & Shutters (L+M) | 57 | Nos | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
9th Floor- Door Frames & Shutters (L) | 57 | Nos | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
10TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
10th Floor- Material Door Hardware | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
10th Floor- Door Frames & Shutters (L+M) | 57 | Nos | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
10th Floor- Door Frames & Shutters (L) | 57 | Nos | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
11TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
11th Floor- Material Door Hardware | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
11th Floor- Door Frames & Shutters (L+M) | 57 | Nos | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
11th Floor- Door Frames & Shutters (L) | 57 | Nos | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
12TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
12th Floor- Material Door Hardware | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
12th Floor- Door Frames & Shutters (L+M) | 57 | Nos | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
12th Floor- Door Frames & Shutters (L) | 57 | Nos | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
13TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
13th Floor- Material Door Hardware | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
13th Floor- Door Frames & Shutters (L+M) | 57 | Nos | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
13th Floor- Door Frames & Shutters (L) | 57 | Nos | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
14TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
14th Floor- Material Door Hardware | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
14th Floor- Door Frames & Shutters (L+M) | 57 | Nos | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
14th Floor- Door Frames & Shutters (L) | 57 | Nos | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
15TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
15th Floor- Material Door Hardware | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
15th Floor- Door Frames & Shutters (L+M) | 57 | Nos | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
15th Floor- Door Frames &amp; Shutters (L) | 57 | Nos | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
16TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
16th Floor- Material Door Hardware | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
16th Floor- Door Frames & Shutters (L+M) | 57 | Nos | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
16th Floor- Door Frames & Shutters (L) | 57 | Nos | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
17TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
17th Floor- Material Door Hardware | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
17th Floor. Door Frames & Shutters (L+M) | 57 | Nos | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
17th Floor- Door Frames & Shutters (L) | 57 | Nos | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
FIRE DOOR WORK | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
FIRE STAIRCASE | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
CORE CUTTING WORK | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Core Cutting Work For Building (Ground to Terrace Floor) | 0 | Job | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
CUSTOMER CHANGES | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
MONTHLY SITE DEPARTMENT LABOUR (CHOICE LIFESTYLE) | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Department Labour- From July 2022 to March 2023 | 9 | Month | 27 Aug 2022 |  | 04 Apr 2023 |  | 0 | 0 | 220 | 0
Department Labour- From April 2023 to March 2024 | 12 | Month | 27 Aug 2022 |  | 04 May 2023 |  | 0 | 0 | 250 | 0
Department Labour- From April 2024 to December 2024 | 9 | Month | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Mathadi Labour- From July 2022 to March 2023 | 9 | Month | 27 Aug 2022 |  | 07 Apr 2023 |  | 0 | 0 | 223 | 0
Mathadi Labour- From April 2023 to March 2024 | 12 | Month | 27 Aug 2022 |  | 04 May 2023 |  | 0 | 0 | 250 | 0
Mathadi Labour- From April 2024 to December 2024 | 9 | Month | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
ALUMINIUM DOORS & WINDOWS (L+M) | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
1ST FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
1st Floor- Aluminium Window & Door (L+M) | 1442.81 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
2ND FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
2nd Floor- Aluminium Window & Door (L+M) | 1442.81 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
3RD FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
3rd Floor- Aluminium Window & Door (L+M) | 1442.81 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
4TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
4th Floor- Aluminium Window & Door (L+M) | 1442.81 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
5TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
5th Floor-Aluminium Window & Door (L+M) | 1442.81 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
6TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
6th Floor-Aluminium Window & Door (L+M) | 1442.81 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
7TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
7th Floor-Aluminium Window & Door (L+M) | 1442.81 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
8TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
8th Floor-Aluminium Window & Door (L+M) | 1442.81 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
9TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
9th Floor-Aluminium Window & Door (L+M) | 1442.81 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
10TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
10th Floor-Aluminium Window & Door (L+M) | 1442.81 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
11TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
11th Floor-Aluminium Window & Door (L+M) | 1442.81 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
12TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
12th Floor-Aluminium Window & Door (L+M) | 1442.81 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
13TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
13th Floor-Aluminium Window & Door (L+M) | 1442.81 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
14TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
14th Floor-Aluminium Window & Door (L+M) | 1442.81 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
15TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
15th Floor-Aluminium Window & Door (L+M) | 1442.81 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
16TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
16th Floor-Aluminium Window & Door (L+M) | 1442.81 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
17TH FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
17th Floor-Aluminium Window & Door (L+M) | 1442.81 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
FABRICATION WORK (L+M) | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
STAIRCASE RAILING WORK (L+M) | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Staircase Railing Work Fire and Regular Staircase (L+M) | 2044 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
BUILDING SERVICES | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Building Services- Fire Fighting Work | 0 | Job | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Building Services- LPG Work | 0 | Job | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Building Services- Solar Water Heater Work | 0 | Job | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Building Services- Fire Fighting Work Temporary GI Sleeves | 0 | No. | 27 Aug 2022 |  | 03 Mar 2023 |  | 0 | 0 | 188 | 0
Building Services- Lifts | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
BUILDING FIXTURES WORK | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Building Fixture Work- Letter Box | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Building Fixture Work- Notice Board | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Building Fixtures- Name Board | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Building Fixtures- Road Safety Equipments | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
EXTRA AMENITIES TO CUSTOMER | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Extra Amenities- Materials | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Extra Amenities- Modular Kitchen Work | 0 | Job | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
CONTRACTOR DEPARTMENT LABOUR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Department Labour- BBM & Plaster Work | 0 | Day | 27 Aug 2022 |  | 02 Jun 2023 |  | 0 | 0 | 279 | 0
Department Labour- Tiling Work | 0 | Day | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Department Labour- Painting Work | 0 | Day | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Department Labour- Gypsum/POP Work | 0 | Day | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Department Labour- Electrical Work | 0 | Day | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Department Labour- Fabrication Work | 0 | Day | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Department Labour- Plumbing Work | 0 | Day | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
SUBSTRUCTURE & SUPERSTRUCTURE COMMON WORK | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Substructure Miscellaneous Work | 0 | No. | 27 Aug 2022 |  | 10 Feb 2023 |  | 0 | 0 | 167 | 0
Plumbing Work Curing Line | 0 | No. | 27 Aug 2022 |  | 10 Feb 2023 |  | 0 | 0 | 167 | 0
B- BUILDING | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
RCC WORK | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
PCC Work - (M15) | 5.27 | Cu.Mtrs | 27 Aug 2022 |  | 15 Jun 2023 |  | 0 | 0 | 292 | 0
Footing - (M30) | 31.39 | Cu.Mtrs | 27 Aug 2022 |  | 15 Jun 2023 |  | 0 | 0 | 292 | 0
Columns - Footing to 1st Slab (M30) | 22.11 | Cu.Mtrs | 27 Aug 2022 |  | 15 Jun 2023 |  | 0 | 0 | 292 | 0
Lift Pardi - Footing to 1st Slab (M30) | 8.02 | Cu.Mtrs | 27 Aug 2022 |  | 15 Jun 2023 |  | 0 | 0 | 292 | 0
Beams - Plinth Beam (M25) | 10.33 | Cu.Mtrs | 27 Aug 2022 |  | 15 Jun 2023 |  | 0 | 0 | 292 | 0
Staircase - Ground to 1st Floor (M25) | 5.02 | Cu.Mtrs | 27 Aug 2022 |  | 15 Jun 2023 |  | 0 | 0 | 292 | 0
Beams - Mezzanine Slab Beam (M25) | 6.85 | Cu.Mtrs | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Slab - Mezzanine Slab (M25) | 8.47 | Cu.Mtrs | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Columns - 1st to 2nd Slab (M30) | 15.82 | Cu.Mtrs | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Lift Pardi - 1st to 2nd Slab (M30) | 4.7 | Cu.Mtrs | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Staircase - 1st floor to 2nd Floor (M25) | 5.19 | Cu.Mtrs | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Beams - 1st Slab Beams (M25) | 18.9 | Cu.Mtrs | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Slab - 1st Slab (M25) | 23.49 | Cu.Mtrs | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Columns - 2nd to 3rd Slab (M30) | 14.66 | Cu.Mtrs | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Lift Pardi - 2nd to 3rd Slab (M30) | 2.21 | Cu.Mtrs | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Staircase - 2nd to Terrace Floor (M25) | 2.51 | Cu.Mtrs | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Columns - 3rd Slab to Terrace Parapet & OHWT Bottom (M30) | 5.35 | Cu.Mtrs | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Columns - OHWT Bottom to OHWT Top (M30) | 1.58 | Cu.Mtrs | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Staircase -2nd to 3rd Floor (M25) | 2.51 | Cu.Mtrs | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
BRICKWORK | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
GROUND FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Ground Floor - 5" AAC Block Work | 20.99 | Cu.Mtrs | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Ground Floor - 6" AAC Block Work | 0.64 | Cu.Mtr | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Ground Floor - 5" Fly Ash Brickwork | 6.35 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Ground Floor - DPC & Patli Work (M20 Site Mix) | 1.59 | Cu.Mtr | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
1ST FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
1st Floor - 5" AAC Block Work | 19.27 | Cu.Mtrs | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
1st Floor - 6" AAC Block Work | 0.64 | Cu.Mtr | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
1st Floor - 5" Fly Ash Brickwork | 12.16 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
1st Floor - DPC & Patli (M20 Site Mix) | 3.63 | Cu.Mtr | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
2ND FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
2nd Floor - 5" AAC Block Work | 16.56 | Cu.Mtrs | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
2nd Floor - 6" AAC Block Work | 0.32 | Cu.Mtr | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
2nd Floor - 5" Fly Ash Brickwork | 8.5 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
2nd Floor - DPC & Patli (M20 Site Mix) | 10.43 | Cu.Mtr | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
TOP TERRACE | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Top Terrace - 6" AAC Block Work | 0.18 | Cu.Mtr | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Top Terrace - DPC & Patli (M20 Site Mix) | 1.81 | Cu.Mtr | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
INTERNAL PLASTER WORK | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Ground Floor - Internal Tar Plaster Work | 201.07 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
1st Floor - Internal Tar Plaster Work | 461.02 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
2nd Floor - Internal Tar Plaster Work | 287.72 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Top Terrace Floor - Internal Tar Plaster Work | 28.09 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
EXTERNAL PLASTER WORK | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
PARKING AREA, TOP TERRACE, STAIRCASE, LMR & OHWT PLASTER | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Parking Area - Material For External Plaster Work | 1179.2 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Top Terrace - Material For External Plaster Work | 2187.89 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Staircase - Material For External Plaster Work | 3206.06 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
LMR & OHWT - Material For External Plaster Work | 567.8 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Labour For - Parking Area, Top Terrace, Staircase, LMR&OHWT | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
NORTH SIDE | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
North Side - Material For External Plaster Work | 1866.69 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
North Side - Labour For External Plaster Work | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
SOUTH SIDE | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
South Side - Material For External Plaster Work | 860.47 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
South Side - Labour For External Plaster Work | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
EAST SIDE | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
East Side - Material For External Plaster Work | 1852.27 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
East Side - Labour For External Plaster Work | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
WEST SIDE | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
West Side - Material For External Plaster Work | 2184.77 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
West Side - Labour For External Plaster Work | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
WATERPROOFING WORK | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Ground Floor - Material For Waterproofing (Toilets) | 21.74 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
1st Floor - Material For Waterproofing (Toilets) | 60.06 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
2nd Floor - Material For Waterproofing (Toilets) | 41.55 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Terrace Floor - Waterproofing At Top Terrace | 1891.02 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
OHWT - Material For Waterproofing Work | 249.4 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Lift Pit- Waterproofing Work | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
TILING WORK | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
GROUND FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Ground Floor Flooring Work | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Ground Floor Granite Work | 0 | R.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Ground Floor Dado Work | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
1ST FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
1st Floor Flooring Work | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
1st Floor Granite Work | 0 | R.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
1st Floor Dado Work | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
2ND FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
2nd Floor Flooring Work | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
2nd Floor Granite Work | 0 | R.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
2nd Floor Dado Work | 0 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
STAIRCASE 1 | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
GROUND FLOOR TO 1ST FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
STAIRCASE 2 | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
GROUND FLOOR TO 2ND FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
INTERNAL PAINTING WORK (L+M) | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
GROUND FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
1ST FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
2ND FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
EXTERNAL PAINTING WORK (L+M) | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
ELECTRICAL WORK | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
GROUND FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
1ST FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
2ND FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
PLUMBING WORK | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
GROUND FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
1ST FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
2ND FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
TERRACE FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
ALUMINIUM DOORS & WINDOWS (L+M) | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
GROUND FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
1ST FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
2ND FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
TERRACE FLOOR | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
FABRICATION WORK | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
STAIRCASE (GROUND FLOOR TO FIRST FLOOR) | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Staircase (Ground Floor to First Floor) Staircase MS Railing | 37.72 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
STAIRCASE (GROUND FLOOR TO TOP TERRACE) | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Staircase (Ground Floor to Top Terrace) Staircase MS Railing | 373.28 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
GYPSUM PUNNING WORK (L+M) | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Ground Floor - Gypsum Punning Work | 2345.37 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
1st Floor - Gypsum Punning Work | 1934.64 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
2nd Floor - Gypsum Punning Work | 1761.31 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Top Terrace - Gypsum Punning Work | 134.87 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
SWIMMING POOL | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Swimming Pool - PCC Work (M15) | 4.71 | Cu.Mtrs | 27 Aug 2022 |  | 01 Jun 2023 |  | 0 | 0 | 278 | 0
Swimming Pool - Raft RCC Work (M25) | 10.18 | Cu.Mtrs | 27 Aug 2022 |  | 01 Jun 2023 |  | 0 | 0 | 278 | 0
Swimming Pool - Column (M25) | 0.68 | Cu.Mtrs | 27 Aug 2022 |  | 01 Jun 2023 |  | 0 | 0 | 278 | 0
Swimming Pool - RCC Pardi (M25) | 5.5 | Cu.Mtrs | 27 Aug 2022 |  | 01 Jun 2023 |  | 0 | 0 | 278 | 0
SITE DEVELOPMENT | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
COMPOUND WALL | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Compound Wall (East & South side)- RCC Work (M20) | 26.3 | Cu.Mtr | 27 Aug 2022 |  | 19 Jan 2023 |  | 0 | 0 | 145 | 0
Compound Wall - RCC Work (Steel) | 2.493 | Tonne | 27 Aug 2022 |  | 19 Jan 2023 |  | 0 | 0 | 145 | 0
Compound Wall (East & South side) - PCC Work-M15 | 6.37 | Cu.Mtr | 27 Aug 2022 |  | 19 Jan 2023 |  | 0 | 0 | 145 | 0
Compound Wall (North side) - PCC Work-M15 | 1.98 | Cu.Mtr | 27 Aug 2022 |  | 18 Feb 2023 |  | 0 | 0 | 175 | 0
Compound Wall (North side)- RCC Work (M20) | 16.65 | Cu.Mtr | 27 Aug 2022 |  | 18 Feb 2023 |  | 0 | 0 | 175 | 0
Trench at Comp. Wall (North & East Side) - PCC Work - M15 | 13.16 | Cu.Mtr | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Compound Wall and Gate Fabrication Work | 0 | No. | 27 Aug 2022 |  | 15 May 2023 |  | 0 | 0 | 261 | 0
Trench at Comp Wall - Waterproof Plaster Work | 4232.4 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Security Cabin & Gate-Ext. Plaster 15-20 mm Thk. | 841.74 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
North Side Compound Wall-Ext. Plaster 15-20 mm Thk. | 1625.69 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
South side Compound Wall-Ext. Plaster 15-20 mm Thk. | 1337.32 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
East Side Compound Wall-Ext. Plaster 15-20 mm Thk. | 2647.94 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
West Side Compound Wall-Ext. Plaster 15-20 mm Thk. | 1762.39 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Compound Wall (South, East & West side)- 5" Fly Ash Brickwor | 5227.67 | Sq.Ft | 27 Aug 2022 |  | 14 Mar 2023 |  | 0 | 0 | 199 | 0
Compound Wall (North side)- 5" Fly Ash Brickwork | 1265.39 | Sq.Ft | 27 Aug 2022 |  | 14 Mar 2023 |  | 0 | 0 | 199 | 0
Trench at Comp. Wall (North & East Side) - 5" Fly Ash Brickw | 1251.42 | Sq.Ft | 27 Aug 2022 |  | 14 Mar 2023 |  | 0 | 0 | 199 | 0
Compound Wall (South, East & West side) - 4" Fly Ash Brickwo | 862.33 | Sq.Ft | 27 Aug 2022 |  | 01 May 2023 |  | 0 | 0 | 247 | 0
Compound Wall (North side) - 4" Fly Ash Brickwork | 251.103 | Sq.Ft | 27 Aug 2022 |  | 01 May 2023 |  | 0 | 0 | 247 | 0
STP/ SEWAGE TREATMENT PLANT | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
STP - RCC Work | 99000 | Ltrs | 27 Aug 2022 |  | 01 Jul 2023 |  | 0 | 0 | 308 | 0
ENTRY GATE & EXIT GATE | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
PODIUM | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
TRANSFORMER ROOM | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Transformer Room - Brickwork | 269 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
UGWT/ UNDERGROUND WATER TANK | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
UGWT RCC Work (M25) | 114.61 | Cu.Mtr | 27 Aug 2022 |  | 01 Oct 2022 |  | 0 | 0 | 35 | 0
UGWT Waterproof Plaster Work (Material) | 2931.9 | Sq.Ft | 27 Aug 2022 |  | 17 Jan 2023 |  | 0 | 0 | 143 | 0
UGWT Waterproof Plaster Work (Labour) | 0 | Job | 27 Aug 2022 |  | 03 Mar 2023 |  | 0 | 0 | 188 | 0
COMMON MEP WORK | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Earthing & CCTV Electrical Work | 0 | No. | 27 Aug 2022 |  | 15 May 2023 |  | 0 | 0 | 261 | 0
MSEB ELECTRICAL | 0 | No. | 27 Aug 2022 |  | 15 May 2023 |  | 0 | 0 | 261 | 0
LANDSCAPE /GARDEN | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
EQUIPMENT & MACHINERIES | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Equipment & Machineries- Owned | 0 | Nos | 27 Aug 2022 |  | 10 Feb 2023 |  | 0 | 0 | 167 | 0
Equipment & Machineries- Hire Charges | 0 | Nos | 27 Aug 2022 |  | 01 Oct 2022 |  | 0 | 0 | 35 | 0
Equipment & Machineries - Repairing Work | 0 | Lumsum | 27 Aug 2022 |  | 02 Jun 2023 |  | 0 | 0 | 279 | 0
ELECTRICAL VEHICLE CHARGING SYSTEM | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
STACK MECHANICAL PARKING | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
LIGHTNING ARRESTER | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
SURVEY | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Survey Work | 0 | Job | 27 Aug 2022 |  | 17 Oct 2022 |  | 0 | 0 | 51 | 0
ROAD WORK | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Road Work (Material) | 0 | Cu.Mtr | 27 Aug 2022 |  | 02 Aug 2023 |  | 0 | 0 | 340 | 0
PAVING BLOCK WORK | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Paving Block Work | 3000 | Sq.Ft | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
PUMP SYSTEM | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
SAFETY WORK | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Safety Work- Safety Net Work | 0 | Job | 27 Aug 2022 |  | 10 Feb 2023 |  | 0 | 0 | 167 | 0
PPE For Management, Staff & Labours | 0 | Nos | 27 Aug 2022 |  | 11 Apr 2023 |  | 0 | 0 | 227 | 0
WATER TANKER | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Water Tanker - From Regular Supplier | 0 | Job | 27 Aug 2022 |  | 01 Jun 2023 |  | 0 | 0 | 278 | 0
Water Tanker - From PMC STP | 0 | Job | 27 Aug 2022 |  | 01 Jul 2023 |  | 0 | 0 | 308 | 0
REPAIR & MAIN EXPENSES | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
EXTERNAL ELECTRICAL | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Miscellaneous Electric Work | 0 | Job | 27 Aug 2022 |  | 15 May 2023 |  | 0 | 0 | 261 | 0
GARBAGE CHUTE | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Garbage Chute - Fabrication Work | 50 | Nos | 27 Aug 2022 |  | 27 Jul 2023 |  | 0 | 0 | 334 | 0
SITE MANAGEMENT | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
SITE OFFICE | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
PETTY CASH | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
September 2022 | 3400 | Rs. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
November 2022 | 16156 | Rs. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
December 2022 | 15503 | Rs. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
January 2023 | 12974 | Rs. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
February 2023 | 25346 | Rs. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
March 2023 | 21780 | Rs. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
May 2023 | 16901 | Rs. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
June 2023 | 37445 | Rs. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
July 2023 | 12776 | Rs. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
GODOWNS | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Temporary Security/Watchman Cabin MS Fabrication Work | 0 | Sq.Ft | 27 Aug 2022 |  | 20 Dec 2022 |  | 0 | 0 | 115 | 0
Temporary Godown For Material Storage | 0 | Sq.Ft | 27 Aug 2022 |  | 03 Mar 2023 |  | 0 | 0 | 188 | 0
BARRICATION | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Barrication- MS Fabrication Work | 0 | No. | 27 Aug 2022 |  | 01 Oct 2022 |  | 0 | 0 | 35 | 0
Entrance Gate - Fabrication Work | 1 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
SECURITY | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Security- From Month July 2022 to March 2023 | 9 | Month | 27 Aug 2022 |  | 07 Sep 2022 |  | 0 | 0 | 11 | 0
Security- For June 2022 | 1 | Month | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Security- From Month April 2023 to March 2024 | 12 | Month | 27 Aug 2022 |  | 04 May 2023 |  | 0 | 0 | 250 | 0
Security- From April 2024 to December 2024 | 9 | Month | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
LABOUR CAMP | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Labour Camp - Fabrication Work (Labour) | 0 | No. | 27 Aug 2022 |  | 09 Sep 2022 |  | 0 | 0 | 13 | 0
Labour Camp - Material | 0 | Job | 27 Aug 2022 |  | 01 Oct 2022 |  | 0 | 0 | 35 | 0
Labour Camp - Contractor Department Labour | 0 | Job | 27 Aug 2022 |  | 02 Jan 2023 |  | 0 | 0 | 128 | 0
Labour Camp - Plumbing work (Material) | 0 | No. | 27 Aug 2022 |  | 10 Feb 2023 |  | 0 | 0 | 167 | 0
Labour Camp - Electrical Work (Material) | 0 | No. | 27 Aug 2022 |  | 11 Apr 2023 |  | 0 | 0 | 227 | 0
Labour Camp Housekeeping Work- From Sept 2022 to Mar 2023 | 7 | Month | 27 Aug 2022 |  | 06 Oct 2022 |  | 0 | 0 | 40 | 0
Labour Camp Housekeeping Work- From April 2023 to Mar 2024 | 12 | Month | 27 Aug 2022 |  | 09 May 2023 |  | 0 | 0 | 255 | 0
Labour Camp Housekeeping Work- From April 2024 to Dec 2024 | 9 | Month | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
WELL EXPENSES | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Well Expenses | 0 | Job | 27 Aug 2022 |  | 01 Oct 2022 |  | 0 | 0 | 35 | 0
Well Slab - Slab, Beam, Col & Pardi (M30) | 68.18 | Cu.Mtr | 27 Aug 2022 |  | 13 Jun 2023 |  | 0 | 0 | 290 | 0
Well- PCC (M15) | 9 | Cu.Mtr | 27 Aug 2022 |  | 01 Jun 2023 |  | 0 | 0 | 278 | 0 | Estimated 6.88 Cu.Mtr updated as per Shubham 6.88 to 9 Cu.Mtr
Well - Fabrication Work | 0 | No. | 27 Aug 2022 |  | 01 Jun 2023 |  | 0 | 0 | 278 | 0
Well - Raft (M30) | 11.66 | Cu.Mtrs | 27 Aug 2022 |  | 01 Jun 2023 |  | 0 | 0 | 278 | 0
COMMON MEP WORK | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
LT/ ELECTRICAL WORK | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Electrical Work for CCTV | 1 | Lumsum | 27 Aug 2022 |  | 15 May 2023 |  | 0 | 0 | 261 | 0
Electrical Works on Lumsum Basis | 1 | Nos | 27 Aug 2022 |  | 15 May 2023 |  | 0 | 0 | 261 | 0
Electrical Work For CCTV | 10 | No. | 27 Aug 2022 |  | 15 May 2023 |  | 0 | 0 | 261 | 0
Electrical Work | 1 | No. | 27 Aug 2022 |  | 29 Jun 2023 |  | 0 | 0 | 306 | 0
PLUMBING WORK | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Plumbing Work For Temporary Line Work | 0 | Job | 27 Aug 2022 |  | 17 Oct 2022 |  | 0 | 0 | 51 | 0
HT/ ELECTRICAL WORK | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
DG / Diesel Generator Work | 1 | Job | 27 Aug 2022 |  | 01 May 2023 |  | 0 | 0 | 247 | 0
SHOW FLAT | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Show Flat- Temporary MS Fabrication Work (Material) | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
DAY CARE CENTER / CRECHE | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Day Care Center / Creche - Plumbing Work (Material) | 0 | Job | 27 Aug 2022 |  | 29 Jun 2023 |  | 0 | 0 | 306 | 0
Day Care Center/Creche Expenses From Jul- 2023 to Mar-2024 | 9 | Month | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Day Care Center/Creche Expenses From Apr-2024 to Dec-2024 | 9 | Month | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
CONSULTANTS | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
PLANNING ARCHITECT | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
LIASONING ARCHITECT | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
FIRE FIGHTING CONSULTANT | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Fire Protection Consultant | 0 | Job | 27 Aug 2022 |  | 23 Jan 2023 |  | 0 | 0 | 149 | 0
STP/ SEWAGE TREATMENT PLANT CONSULTANT | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
ERP CONSULTANT | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
CA/ CHARTERED ACCOUNTANT- INCOME TAX | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
CA/ CHARTERED ACCOUNTANT- GOODS AND SERVICE TAX | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
EC/ ENVIRONMENT CLEARANCE | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
MEP CONSULTANTS | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Electrical Consultant | 0 | Job | 27 Aug 2022 |  | 03 Oct 2022 |  | 0 | 0 | 37 | 0
Plumbing Consultant | 0 | Job | 27 Aug 2022 |  | 03 Oct 2022 |  | 0 | 0 | 37 | 0
SAFETY CONSULTANT | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Safety Consultancy Work- February 2023 to March 2023 | 2 | Month | 27 Aug 2022 |  | 20 Apr 2023 |  | 0 | 0 | 236 | 0
Safety Consultancy Work- April 2023 to March 2024 | 12 | Month | 27 Aug 2022 |  | 20 Apr 2023 |  | 0 | 0 | 236 | 0
Safety Consultancy Work- April 2024 to December 2024 | 9 | Month | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
SALES OFFICE & SHOW FLAT | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
SALES OFFICE | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
MASONRY WORK | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Sales Office- BBM Work (Labour) | 0 | Sq.Ft | 27 Aug 2022 |  | 20 Oct 2022 |  | 0 | 0 | 54 | 0
INTERNAL PLASTER | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Sales Office- Internal Plaster Work (Labour) | 0 | Sq.Ft | 27 Aug 2022 |  | 20 Oct 2022 |  | 0 | 0 | 54 | 0
PLUMBING | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Plumbing Work (Material) | 0 | No. | 27 Aug 2022 |  | 11 Apr 2023 |  | 0 | 0 | 227 | 0
LANDSCAPE & GARDEN | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Sales Office Landscape Work | 0 | Job | 27 Aug 2022 |  | 24 Aug 2022 |  | 0 | 0 | 0 | 0
HOUSEKEEPING | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Housekeeping- From Month August 2022 to March 2023 | 8 | Month | 27 Aug 2022 |  | 19 Sep 2022 |  | 0 | 0 | 23 | 0
Housekeeping- From Month April 2023 to March 2024 | 12 | Month | 27 Aug 2022 |  | 08 May 2023 |  | 0 | 0 | 254 | 0
Housekeeping- From Month April 2024 to December 2024 | 9 | Month | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
PETTY CASH | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
October -2022 | 3823 | Rs. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
November 2022 | 4695 | Rs. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
December 2022 | 7276 | Rs. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
January 2023 | 5717 | Rs. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
February 2023 | 5000 | Rs. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Petty Cash - From Feb 2022 to Mar2023 | 2 | Month | 27 Aug 2022 |  | 01 Mar 2023 |  | 0 | 0 | 186 | 0
Petty Cash - From April 2023 to Mar2024 | 12 | Month | 27 Aug 2022 |  | 01 Mar 2023 |  | 0 | 0 | 186 | 0
March 2023 | 9754 | Rs. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
June 2023 | 7738 | Rs. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
July 2023 | 8343 | Rs. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
ELECTRICAL WORK | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
SHOW FLAT (FLAT NO.106) | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
ELECTRICAL WORK | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Show Flat (Flat No.106) - Extra Electrical Work | 0 | Nos | 27 Aug 2022 |  | 05 Jul 2023 |  | 0 | 0 | 312 | 0
PLUMBING WORK | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Sample Flat (Flat No.106)- Plumbing Work (Material) | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
SAMPLE FLAT (FLAT NO.105) | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
PLUMBING WORK | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Sample Flat (Flat No.105)- Plumbing Work (Material) | 0 | No. | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
DOORS | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Doors- (Material) | 0 | Nos | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
SALARY FOR ENGINEER | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Salary For Engineer- From July 2022 to March 2023 | 9 | Month | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Salary For Engineer - From April 2023 to March 2024 | 12 | Month | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Salary For Engineer - From April 2024 to Dec 2024 | 9 | Month | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
QUALITY CONTROL | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Quality Control & Testing | 0 | Nos | 27 Aug 2022 |  | 10 Nov 2022 |  | 0 | 0 | 75 | 0
OTHER THAN CONSTRUCTION COST | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Misc.Work - Other than Construction Cost | 0 | Job | 27 Aug 2022 |  | 04 May 2023 |  | 0 | 0 | 250 | 0
CORPORATION & OTHER CHALLAN | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Corporation & Other Challan | 0 | Job | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
SALES, ADVERTISING & MARKETING | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
SALES, ADVERTISING & MARKETING | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Sales, Advertising & Marketing | 0 | Job | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
RERA/ REAL ESTATE REGULATORY AUTHORITY | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
RERA Registration Charges | 0 | Job | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
SITE ACQUISITION | 0 | No Unit | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0
Land Cost | 0 | Job | 27 Aug 2022 |  |  |  | 0 | 0 | 0 | 0