## Task Details638270916983313166_
Task Details
Project Name : GME- BASEMENT
Task Name : All
Total Records: 47 Records 1 to 47
Page 1 of 1
Task (1) | Qty (2) | Unit (3) | Planned Start (4) | Planned Finish (5) | Actual Start (6) | Actual Finish (7) | Planned Duration (8)=(4)-(5) Days | Actual Duration (9)=(6)-(7) Days | Start Variance (10)=(4)-(6) Days | Finish Variance (11)=(4)-(5) Days | Remark
GME- BASEMENT | 0 | No Unit | 15 Apr 2023 |  |  |  | 0 | 0 | 0 | 0
EARTHWORK | 0 | No Unit | 15 Apr 2023 |  |  |  | 0 | 0 | 0 | 0
Earthwork Excavation in Soft Rock | 36910 | Cum. | 15 Apr 2023 |  | 10 May 2023 |  | 0 | 0 | 25 | 0
RCC WORK | 0 | No Unit | 15 Apr 2023 |  |  |  | 0 | 0 | 0 | 0
RCC Work for Advance Payment | 0 | Sq.ft | 15 Apr 2023 |  | 07 Jun 2023 |  | 0 | 0 | 53 | 0
Retaining Wall PCC As Per Drawing(M15) | 135.35 | Cum. | 15 Apr 2023 |  | 04 Jul 2023 |  | 0 | 0 | 80 | 0
Retaining Wall PCC Extra on Site (M15) | 195 | Cum. | 15 Apr 2023 |  | 08 Jul 2023 |  | 0 | 0 | 84 | 0
Retaining Wall Raft (M25) | 455.83 | Cum. | 15 Apr 2023 |  | 07 Jun 2023 |  | 0 | 0 | 53 | 0
Retaining Wall (M25) | 653.97 | Cum. | 15 Apr 2023 |  | 07 Jun 2023 |  | 0 | 0 | 53 | 0
Retaining Wall Extra on Site (M25) | 327 | Cum. | 15 Apr 2023 |  | 08 Jul 2023 |  | 0 | 0 | 84 | 0
Basement/Podium Column PCC Work (M15) | 10.726 | Cum. | 15 Apr 2023 |  | 12 Jul 2023 |  | 0 | 0 | 88 | 0
Basement/Podium Footing (M25) | 47.3 | Cum. | 15 Apr 2023 |  | 08 Jul 2023 |  | 0 | 0 | 84 | 0
Basement/Podium Column From Footing to 1st Slab (M25) | 111.77 | Cum. | 15 Apr 2023 |  | 08 Jul 2023 |  | 0 | 0 | 84 | 0
Basement Tie Beams (M30) | 108.25 | Cum. | 15 Apr 2023 |  | 08 Jul 2023 |  | 0 | 0 | 84 | 0
Below Basement Raft PCC Work (M15) | 405.74 | Cum. | 15 Apr 2023 |  | 04 Jul 2023 |  | 0 | 0 | 80 | 0
Basement 1st Slab (M25) | 0 | Cum. | 15 Apr 2023 |  |  |  | 0 | 0 | 0 | 0
Basement Raft (M30) | 811.47 | Cum. | 15 Apr 2023 |  | 07 Jun 2023 |  | 0 | 0 | 53 | 0
Basement Trimix Work (M15) | 0 | Cum. | 15 Apr 2023 |  | 08 Jul 2023 |  | 0 | 0 | 84 | 0
WATERPROOFING WORK (L+M) | 0 | No Unit | 15 Apr 2023 |  |  |  | 0 | 0 | 0 | 0
Basement Floor- Waterproofing Work | 0 | Sq.ft | 15 Apr 2023 |  | 25 May 2023 |  | 0 | 0 | 40 | 0
Basement Floor RW Waterproofing Work | 0 | Sq.ft | 15 Apr 2023 |  |  |  | 0 | 0 | 0 | 0
MASONRY WORK | 0 | No Unit | 15 Apr 2023 |  |  |  | 0 | 0 | 0 | 0
Trench Line Brick Work (Material) | 0 | Sq.ft | 15 Apr 2023 |  | 25 Jul 2023 |  | 0 | 0 | 101 | 0
INTERNAL PLASTER WORK | 0 | No Unit | 15 Apr 2023 |  |  |  | 0 | 0 | 0 | 0
Basement Floor - Material For Internal Plaster Work | 0 | Sq.ft | 15 Apr 2023 |  |  |  | 0 | 0 | 0 | 0
Basement Floor - Labour For Plaster Work | 0 | Sq.ft | 15 Apr 2023 |  |  |  | 0 | 0 | 0 | 0
CORE CUTTING WORK | 0 | No Unit | 15 Apr 2023 |  |  |  | 0 | 0 | 0 | 0
Basement Floor- Core Cutting Work | 0 | Job | 15 Apr 2023 |  |  |  | 0 | 0 | 0 | 0
FABRICATION WORK | 0 | No Unit | 15 Apr 2023 |  |  |  | 0 | 0 | 0 | 0
Basement Floor- Tank Doors Fabrication Work | 0 | No. | 15 Apr 2023 |  |  |  | 0 | 0 | 0 | 0
Basement Floor - Trench Fabrication Work | 0 | Job | 15 Apr 2023 |  |  |  | 0 | 0 | 0 | 0
TILING WORK | 0 | No Unit | 15 Apr 2023 |  |  |  | 0 | 0 | 0 | 0
Basement Floor - Entrance Lobby Flooring | 0 | Sq.ft | 15 Apr 2023 |  |  |  | 0 | 0 | 0 | 0
INTERNAL PAINTING WORK (L+M) | 0 | No Unit | 15 Apr 2023 |  |  |  | 0 | 0 | 0 | 0
Basement Floor- Internal Painting Work (L+M) | 0 | Sq.ft | 15 Apr 2023 |  |  |  | 0 | 0 | 0 | 0
EXTERNAL PAINTING WORK (L+M) | 0 | No Unit | 15 Apr 2023 |  |  |  | 0 | 0 | 0 | 0
Basement Floor - External Painting Work | 0 | Sq.ft | 15 Apr 2023 |  |  |  | 0 | 0 | 0 | 0
GYPSUM PUNNING WORK (L+M) | 0 | No Unit | 15 Apr 2023 |  |  |  | 0 | 0 | 0 | 0
Basement Floor- Gypsum Punning Work (L+M) | 0 | Sq.ft | 15 Apr 2023 |  |  |  | 0 | 0 | 0 | 0
ELECTRICAL WORK | 0 | No Unit | 15 Apr 2023 |  |  |  | 0 | 0 | 0 | 0
Basement Floor- Electrical Work (Material) | 0 | Per Floor | 15 Apr 2023 |  |  |  | 0 | 0 | 0 | 0
EQUIPMENT & MACHINERIES | 0 | No Unit | 15 Apr 2023 |  |  |  | 0 | 0 | 0 | 0
Pump Repairs | 0 | No. | 15 Apr 2023 |  | 31 Jul 2023 |  | 0 | 0 | 107 | 0
Machinery Hire Charges | 0 | No. | 15 Apr 2023 |  | 05 Jun 2023 |  | 0 | 0 | 51 | 0
Equipment & Machineries- Owned | 0 | Nos | 15 Apr 2023 |  | 29 Jul 2023 |  | 0 | 0 | 105 | 0
CONTRACTORS DEPARTMENT LABOUR | 0 | No Unit | 15 Apr 2023 |  |  |  | 0 | 0 | 0 | 0
Department Labour - BBM & Plaster Work | 0 | Nos | 15 Apr 2023 |  | 12 Jun 2023 |  | 0 | 0 | 58 | 0