## Task Details638270917953107892_
Task Details
Project Name : GME- PROJECT DEVELOPMENT
Task Name : GME- PROJECT DEVELOPMENT
Total Records: 42 Records 1 to 42
Page 1 of 1
Task (1) | Qty (2) | Unit (3) | Planned Start (4) | Planned Finish (5) | Actual Start (6) | Actual Finish (7) | Planned Duration (8)=(4)-(5) Days | Actual Duration (9)=(6)-(7) Days | Start Variance (10)=(4)-(6) Days | Finish Variance (11)=(4)-(5) Days | Remark
GME- PROJECT DEVELOPMENT | 0 | No Unit | 15 Apr 2023 |  |  |  | 0 | 0 | 0 | 0
OPEN SPACE (PODIUM & CLUB HOUSE) | 0 | No Unit | 15 Apr 2023 |  |  |  | 0 | 0 | 0 | 0
RCC WORK | 0 | No Unit | 15 Apr 2023 |  |  |  | 0 | 0 | 0 | 0
Podium Pile PCC Work (M15) | 0.61 | Cum. | 15 Apr 2023 |  | 08 Jul 2023 |  | 0 | 0 | 84 | 0
Podium Pile Column Upto Pile Cap(M25) | 61.39 | Cum. | 15 Apr 2023 |  | 08 Jul 2023 |  | 0 | 0 | 84 | 0
Podium Pile Cap(M25) | 25.9 | Cum. | 15 Apr 2023 |  | 08 Jul 2023 |  | 0 | 0 | 84 | 0
Podium Pile Tie Beam (M25) | 20.01 | Cum. | 15 Apr 2023 |  | 08 Jul 2023 |  | 0 | 0 | 84 | 0
Podium Columns From Pile Cap to 1st Slab (M25) | 18.32 | Cum. | 15 Apr 2023 |  | 08 Jul 2023 |  | 0 | 0 | 84 | 0
Podium Tie Beams - 1st Slab Level (M25) | 0 | Cum. | 15 Apr 2023 |  | 08 Jul 2023 |  | 0 | 0 | 84 | 0
Podium Columns From 1st Slab Tie Beams to 2nd Slab (M25) | 18.32 | Cum. | 15 Apr 2023 |  | 08 Jul 2023 |  | 0 | 0 | 84 | 0
Podium 2nd Slab (M25) | 0 | Cum. | 15 Apr 2023 |  | 08 Jul 2023 |  | 0 | 0 | 84 | 0
Podium Piling RCC Work (Labour) | 0 | Rmt | 15 Apr 2023 |  | 01 Aug 2023 |  | 0 | 0 | 108 | 0
FEATURE WALL | 0 | No Unit | 15 Apr 2023 |  |  |  | 0 | 0 | 0 | 0
CONTRACTORS DEPARTMENT LABOUR | 0 | No Unit | 15 Apr 2023 |  |  |  | 0 | 0 | 0 | 0
Department Labour- BBM & Plaster Work. | 0 | No. | 15 Apr 2023 |  | 07 Jul 2023 |  | 0 | 0 | 83 | 0
MASONRY WORK | 0 | No Unit | 15 Apr 2023 |  |  |  | 0 | 0 | 0 | 0
Feature Wall - 5" FlyAsh Brickwork (Material) | 0 | Sq.ft | 15 Apr 2023 |  |  |  | 0 | 0 | 0 | 0
RCC WORK | 0 | No Unit | 15 Apr 2023 |  |  |  | 0 | 0 | 0 | 0
RCC Work- Feature Wall | 0 | Sq.ft | 15 Apr 2023 |  | 06 Aug 2023 |  | 0 | 0 | 113 | 0
QUALITY CONTROL | 0 | No Unit | 15 Apr 2023 |  |  |  | 0 | 0 | 0 | 0
Quality Control & Testing | 0 | Job | 15 Apr 2023 |  | 21 Jul 2023 |  | 0 | 0 | 97 | 0
CONSULTANTS | 0 | No Unit | 15 Apr 2023 |  |  |  | 0 | 0 | 0 | 0
PLANNING ARCHITECT | 0 | No Unit | 15 Apr 2023 |  |  |  | 0 | 0 | 0 | 0
LIASONING ARCHITECT | 0 | No Unit | 15 Apr 2023 |  |  |  | 0 | 0 | 0 | 0
FIRE FIGHTING CONSULTANT | 0 | No Unit | 15 Apr 2023 |  |  |  | 0 | 0 | 0 | 0
STP/ SEWAGE TREATMENT PLANT CONSULTANT | 0 | No Unit | 15 Apr 2023 |  |  |  | 0 | 0 | 0 | 0
ERP CONSULTANT | 0 | No Unit | 15 Apr 2023 |  |  |  | 0 | 0 | 0 | 0
CA/ CHARTERED ACCOUNTANT- INCOME TAX | 0 | No Unit | 15 Apr 2023 |  |  |  | 0 | 0 | 0 | 0
CA/ CHARTERED ACCOUNTANT- GOODS AND SERVICE TAX | 0 | No Unit | 15 Apr 2023 |  |  |  | 0 | 0 | 0 | 0
EC/ ENVIRONMENT CLEARANCE | 0 | No Unit | 15 Apr 2023 |  |  |  | 0 | 0 | 0 | 0
MEP CONSULTANTS | 0 | No Unit | 15 Apr 2023 |  |  |  | 0 | 0 | 0 | 0
SAFETY CONSULTANT | 0 | No Unit | 15 Apr 2023 |  |  |  | 0 | 0 | 0 | 0
SALES, ADVERTISING & MARKETING | 0 | No Unit | 15 Apr 2023 |  |  |  | 0 | 0 | 0 | 0
SURVEY | 0 | No Unit | 15 Apr 2023 |  |  |  | 0 | 0 | 0 | 0
SURVEY Survey Work | 0 | Job | 15 Apr 2023 |  | 27 Jul 2023 |  | 0 | 0 | 103 | 0
COMPOUND WALL | 0 | No Unit | 15 Apr 2023 |  |  |  | 0 | 0 | 0 | 0
ENTRY GATE & EXIT GATE | 0 | No Unit | 15 Apr 2023 |  |  |  | 0 | 0 | 0 | 0
COMMON MEP WORK | 0 | No Unit | 15 Apr 2023 |  |  |  | 0 | 0 | 0 | 0
Earthing & CCTV Electrical Work | 0 | No. | 15 Apr 2023 |  |  |  | 0 | 0 | 0 | 0
MSEB Electrical | 0 | No. | 15 Apr 2023 |  |  |  | 0 | 0 | 0 | 0
LANDSCAPE /GARDEN | 0 | No Unit | 15 Apr 2023 |  |  |  | 0 | 0 | 0 | 0
STACK MECHANICAL PARKING | 0 | No Unit | 15 Apr 2023 |  |  |  | 0 | 0 | 0 | 0