## Task Details638270918494367684_
Task Details
Project Name : GME- SAMPLE FLAT & SALES OFFICE
Task Name : GME- SAMPLE FLAT & SALES OFFICE
Total Records: 25 Records 1 to 25
Page 1 of 1
Task (1) | Qty (2) | Unit (3) | Planned Start (4) | Planned Finish (5) | Actual Start (6) | Actual Finish (7) | Planned Duration (8)=(4)-(5) Days | Actual Duration (9)=(6)-(7) Days | Start Variance (10)=(4)-(6) Days | Finish Variance (11)=(4)-(5) Days | Remark
GME- SAMPLE FLAT & SALES OFFICE | 0 | No Unit | 15 Apr 2023 |  |  |  | 0 | 0 | 0 | 0
SAMPLE FLAT | 0 | No Unit | 15 Apr 2023 |  |  |  | 0 | 0 | 0 | 0
SALES OFFICE | 0 | No Unit | 15 Apr 2023 |  |  |  | 0 | 0 | 0 | 0
HVAC | 0 | No Unit | 15 Apr 2023 |  |  |  | 0 | 0 | 0 | 0
HVAC AC Repairing Work | 0 | Rs. | 15 Apr 2023 |  | 26 May 2023 |  | 0 | 0 | 41 | 0
CONTRACTORS DEPARTMENT LABOUR | 0 | No Unit | 15 Apr 2023 |  |  |  | 0 | 0 | 0 | 0
Department Labour- RCC Work. | 0 | No. | 15 Apr 2023 |  | 27 May 2023 |  | 0 | 0 | 42 | 0
Department Labour- BBM & Plaster Work | 0 | Day | 15 Apr 2023 |  | 07 Aug 2023 |  | 0 | 0 | 114 | 0
EQUIPMENT & MACHINERIES | 0 | No Unit | 15 Apr 2023 |  |  |  | 0 | 0 | 0 | 0
Machinery Hire Charges | 0 | No. | 15 Apr 2023 |  | 05 Jun 2023 |  | 0 | 0 | 51 | 0
MASONRY WORK | 0 | No Unit | 15 Apr 2023 |  |  |  | 0 | 0 | 0 | 0
Sales Office Foundation - Masonry Work | 0 | Sft. | 15 Apr 2023 |  |  |  | 0 | 0 | 0 | 0
ELECTRICAL WORK | 0 | No Unit | 15 Apr 2023 |  |  |  | 0 | 0 | 0 | 0
Electrical Work | 0 | Sft. | 15 Apr 2023 |  |  |  | 0 | 0 | 0 | 0
CONICAL TENSILE SHED | 0 | No Unit | 15 Apr 2023 |  |  |  | 0 | 0 | 0 | 0
Conical Tensile Shed Conical Tensile Shed | 0 | Sq.ft | 15 Apr 2023 |  | 31 Jul 2023 |  | 0 | 0 | 107 | 0
FURNITURE | 0 | No Unit | 15 Apr 2023 |  |  |  | 0 | 0 | 0 | 0
Furniture Sofa and Chairs Shampooing Work | 0 | Job | 15 Apr 2023 |  |  |  | 0 | 0 | 0 | 0
HOUSEKEEPING | 0 | No Unit | 15 Apr 2023 |  |  |  | 0 | 0 | 0 | 0
Housekeeping From Month May 2023 to March 2024 | 11 | Month. | 15 Apr 2023 |  | 04 Aug 2023 |  | 0 | 0 | 111 | 0
Housekeeping From Month April 2024 to March 2025 | 12 | Month. | 15 Apr 2023 |  |  |  | 0 | 0 | 0 | 0
RCC WORK | 0 | No Unit | 15 Apr 2023 |  |  |  | 0 | 0 | 0 | 0
RCC Work- Only for Steel Requisition Purpose | 0 | Ton | 15 Apr 2023 |  | 06 Aug 2023 |  | 0 | 0 | 113 | 0
LANDSCAPE | 0 | No Unit | 15 Apr 2023 |  |  |  | 0 | 0 | 0 | 0
Sales Office Landscape Work | 0 | Lumsum | 15 Apr 2023 |  | 06 Aug 2023 |  | 0 | 0 | 113 | 0